## Import
Activity ID | Activity Name | WBS Code | Discipline | Area | BL Start | BL Finish | Start | Finish | Planned Duration | Budgeted Labor Units | Physical % Complete | Activity Status | Data Date
A0001 | Civil work package 001 | WBS.01.01 | Civil | Area A | 2025-06-16 | 2025-11-07 | 2025-06-16 |  | 144 | 1339 | 1.08 | In Progress | 2025-09-30
A0002 | Mechanical work package 002 | WBS.01.01 | Mechanical | Area A | 2025-01-14 | 2025-06-09 | 2025-01-14 |  | 146 | 1511.8 | 0.96 | Complete | 2025-09-30
A0003 | Piping work package 003 | WBS.01.01 | Piping | Area A | 2025-07-10 | 2025-07-05 | 2025-07-10 |  | 64 | 1132.4 | 0.96 | In Progress | 2025-09-30
A0004 | Electrical work package 004 | WBS.01.01 |  | Area A | 2025-04-01 | 2025-07-01 | 2025-04-01 |  | 91 | 1099 | 0.96 | In Progress | 2025-09-30
A0001 | Instrumentation work package 005 | WBS.01.01 | Instrumentation | Area A | 2025-10-27 | 2026-01-17 |  |  | 82 | 289.9 | 0 | Not Started | 2025-09-30
A0006 | Civil work package 006 | WBS.01.01 | Civil | Area B | 2025-08-29 | 2025-10-20 | 2025-08-29 |  | 52 | 1747.7 | 0.6068 | In Progress | 2025-09-30
A0007 | Mechanical work package 007 | WBS.01.01 | Mechanical | Area B | 2025-06-22 | 2025-08-23 | 2025-06-22 |  | 62 | 1505.4 | 0.96 | In Progress | 2025-09-30
A0008 | Piping work package 008 | WBS.01.01 | Piping | Area B | 2025-02-07 | 2025-07-05 | 2025-02-07 |  | 148 | 1408.3 | 0.96 | In Progress | 2025-09-30
A0009 | Electrical work package 009 | WBS.01.01 | Electrical | Area B | 2026-01-12 | 2026-04-26 |  |  | 104 | 649.1 | 0 | Not Started | 2025-09-30
A0010 | Instrumentation work package 010 | WBS.01.01 | Instrumentation | Area B | 2026-01-22 | 2026-04-18 |  |  | 86 | 285.7 | 0 | Not Started | 2025-09-30
A0011 | Civil work package 011 | WBS.01.02 | Civil | Area C | 2025-08-18 | 2025-11-07 | 2025-08-18 |  | 81 | 123.7 | 0.3988 | In Progress | 2025-09-30
A0012 | Mechanical work package 012 | WBS.01.02 | Mechanical | Area C | 2026-01-31 | 2026-03-31 |  |  | 59 | 785.9 | 0 | Not Started | 2025-09-30
A0013 | Piping work package 013 | WBS.01.02 | Piping | Area C | 2025-12-17 | 2026-02-07 |  |  | 52 | 1615.2 | 0 | Not Started | 2025-09-30
A0014 | Electrical work package 014 | WBS.01.02 | Electrical | Area C | 2025-12-23 | 2026-05-05 |  |  | 133 | 92 | 0 | Not Started | 2025-09-30
A0015 | Instrumentation work package 015 | WBS.01.02 | Instrumentation | Area C | 2026-02-15 | 2026-04-24 |  |  | 68 | 972.3 | 0 | Not Started | 2025-09-30
A0016 | Civil work package 016 | WBS.01.02 | Civil | Area A | 2025-05-08 | 2025-06-11 | 2025-05-08 |  | 34 | 1128.5 | 0.96 | In Progress | 2025-09-30
A0017 | Mechanical work package 017 | WBS.01.02 | Mechanical | Area A | 2026-03-05 | 2026-05-03 |  |  | 59 | 1236.1 | 0 | Not Started | 2025-09-30
A0018 | Piping work package 018 | WBS.01.02 | Piping | Area A | 2025-10-05 | 2026-01-07 |  |  | 94 | 235.3 | 0 | Not Started | 2025-09-30
A0019 | Electrical work package 019 | WBS.01.02 | Electrical | Area A | 2025-10-24 | 2025-11-24 |  |  | 31 | 960.8 | 0 | Not Started | 2025-09-30
A0020 | Instrumentation work package 020 | WBS.01.02 | Instrumentation | Area A | 2026-02-12 | 2026-03-30 |  |  | 46 | 666.6 | 0 | Not Started | 2025-09-30
A0021 | Civil work package 021 | WBS.01.03 | Civil | Area B | 2025-08-21 | 2025-10-19 | 2025-08-21 |  | 59 | 240.1 | 0.6628 | In Progress | 2025-09-30
A0022 | Mechanical work package 022 | WBS.01.03 | Mechanical | Area B | 2025-11-14 | 2026-03-31 |  |  | 137 | 1605.8 | 0 | Not Started | 2025-09-30
A0023 | Piping work package 023 | WBS.01.03 | Piping | Area B | 2025-01-08 | 2025-02-26 | 2025-01-08 | 2025-02-26 | 49 | 1023.8 | 0.9988 | Complete | 2025-09-30
A0024 | Electrical work package 024 | WBS.01.03 | Electrical | Area B | 2025-05-25 | 2025-09-21 | 2025-05-25 | 2025-09-21 | 119 | 1197.4 | 0.9965 | Complete | 2025-09-30
A0025 | Instrumentation work package 025 | WBS.01.03 | Instrumentation | Area B | 2025-04-30 | 2025-06-28 | 2025-04-30 |  | 59 | 1753.6 | 0.96 | In Progress | 2025-09-30
A0026 | Civil work package 026 | WBS.01.03 | Civil | Area C | 2025-09-11 | 2025-12-09 | 2025-09-11 |  | 89 | 415.8 | 0.2284 | In Progress | 2025-09-30
A0027 | Mechanical work package 027 | WBS.01.03 | Mechanical | Area C | 2025-01-12 | 2025-06-02 | 2025-01-12 | 2025-06-02 | 141 | 816.5 | 1 | Complete | 2025-09-30
A0028 | Piping work package 028 | WBS.01.03 | Piping | Area C | 2025-03-19 | 2025-06-23 | 2025-03-19 |  | 96 | 1690.2 | 0.96 | In Progress | 2025-09-30
A0029 | Electrical work package 029 | WBS.01.03 | Electrical | Area C | 2026-01-18 | 2026-05-16 |  |  | 118 | 1278.9 | 0 | Not Started | 2025-09-30
A0030 | Instrumentation work package 030 | WBS.01.03 | Instrumentation | Area C | 2026-01-13 | 2026-06-01 |  |  | 139 | 959.5 | 0 | Not Started | 2025-09-30
A0031 | Civil work package 031 | WBS.01.04 | Civil | Area A | 2026-01-23 | 2026-04-03 |  |  | 70 | 726 | 0 | Not Started | 2025-09-30
A0032 | Mechanical work package 032 | WBS.01.04 | Mechanical | Area A | 2025-05-09 | 2025-08-17 | 2025-05-09 |  | 100 | 132.5 | 0.96 | In Progress | 2025-09-30
A0033 | Piping work package 033 | WBS.01.04 | Piping | Area A | 2025-12-03 | 2026-01-27 |  |  | 55 | 1151.4 | 0 | Not Started | 2025-09-30
A0034 | Electrical work package 034 | WBS.01.04 | Electrical | Area A | 2025-11-14 | 2026-04-10 |  |  | 147 | 968 | 0 | Not Started | 2025-09-30
A0035 | Instrumentation work package 035 | WBS.01.04 | Instrumentation | Area A | 2025-01-16 | 2025-06-10 | 2025-01-16 |  | 145 | 1517.9 | 0.9637 | In Progress | 2025-09-30
A0036 | Civil work package 036 | WBS.01.04 | Civil | Area B | 2025-08-30 | 2025-12-23 | 2025-08-30 |  | 115 | 1215.5 | 0.2263 | In Progress | 2025-09-30
A0037 | Mechanical work package 037 | WBS.01.04 | Mechanical | Area B | 2025-06-08 | 2025-10-06 | 2025-06-08 |  | 120 | 104.8 | 0.8029 | In Progress | 2025-09-30
A0038 | Piping work package 038 | WBS.01.04 | Piping | Area B | 2025-08-05 | 2025-10-30 | 2025-08-05 |  | 86 | 377.9 | 0.6022 | In Progress | 2025-09-30
A0039 | Electrical work package 039 | WBS.01.04 | Electrical | Area B | 2025-06-16 | 2025-09-29 | 2025-06-16 | 2025-09-29 | 105 | 945.4 | 1 | Complete | 2025-09-30
A0040 | Instrumentation work package 040 | WBS.01.04 | Instrumentation | Area B | 2025-01-17 | 2025-04-27 | 2025-01-17 |  | 100 | 1697.2 | 0.96 | In Progress | 2025-09-30
A0041 | Civil work package 041 | WBS.01.05 | Civil | Area C | 2026-02-14 | 2026-05-01 |  |  | 76 | 1733.2 | 0 | Not Started | 2025-09-30
A0042 | Mechanical work package 042 | WBS.01.05 | Mechanical | Area C | 2026-01-04 | 2026-02-05 |  |  | 32 | 1480.9 | 0 | Not Started | 2025-09-30
A0043 | Piping work package 043 | WBS.01.05 | Piping | Area C | 2025-11-18 | 2026-03-24 |  |  | 126 | 565.1 | 0 | Not Started | 2025-09-30
A0044 | Electrical work package 044 | WBS.01.05 | Electrical | Area C | 2025-06-14 | 2025-10-15 | 2025-06-14 |  | 123 | 666.2 | 0.9283 | In Progress | 2025-09-30
A0045 | Instrumentation work package 045 | WBS.01.05 | Instrumentation | Area C | 2025-02-19 | 2025-07-07 | 2025-02-19 | 2025-07-07 | 138 | 949 | 1 | Complete | 2025-09-30
A0046 | Civil work package 046 | WBS.01.05 | Civil | Area A | 2026-02-18 | 2026-05-27 |  |  | 98 | 1166.8 | 0 | Not Started | 2025-09-30
A0047 | Mechanical work package 047 | WBS.01.05 | Mechanical | Area A | 2025-12-12 | 2026-04-15 |  |  | 124 | 236.9 | 0 | Not Started | 2025-09-30
A0048 | Piping work package 048 | WBS.01.05 | Piping | Area A | 2025-06-05 | 2025-07-19 | 2025-06-05 |  | 44 | 325.9 | 0.9825 | In Progress | 2025-09-30
A0049 | Electrical work package 049 | WBS.01.05 | Electrical | Area A | 2025-02-06 | 2025-06-14 | 2025-02-06 |  | 128 | 1294.7 | 0.96 | In Progress | 2025-09-30
A0050 | Instrumentation work package 050 | WBS.01.05 | Instrumentation | Area A | 2025-12-06 | 2026-03-13 |  |  | 97 | 809.7 | 0 | Not Started | 2025-09-30
A0051 | Civil work package 051 | WBS.02.01 | Civil | Area B | 2025-01-30 | 2025-03-15 | 2025-01-30 |  | 44 | 282.1 | 0.9794 | In Progress | 2025-09-30
A0052 | Mechanical work package 052 | WBS.02.01 | Mechanical | Area B | 2025-05-08 | 2025-09-19 | 2025-05-08 | 2025-09-19 | 134 | 464.6 | 1 | Complete | 2025-09-30
A0053 | Piping work package 053 | WBS.02.01 | Piping | Area B | 2026-02-26 | 2026-05-29 |  |  | 92 | 1162.6 | 0 | Not Started | 2025-09-30
A0054 | Electrical work package 054 | WBS.02.01 | Electrical | Area B | 2025-01-25 | 2025-03-29 | 2025-01-25 | 2025-03-29 | 63 | 1714.7 | 1 | Complete | 2025-09-30
A0055 | Instrumentation work package 055 | WBS.02.01 | Instrumentation | Area B | 2025-07-24 | 2025-10-04 | 2025-07-24 |  | 72 | 1083.9 | 0.7769 | In Progress | 2025-09-30
A0056 | Civil work package 056 | WBS.02.01 | Civil | Area C | 2025-10-27 | 2025-12-15 |  |  | 49 | 1646.8 | 0 | Not Started | 2025-09-30
A0057 | Mechanical work package 057 | WBS.02.01 | Mechanical | Area C | 2026-03-06 | 2026-04-23 |  |  | 48 | 1101.9 | 0 | Not Started | 2025-09-30
A0058 | Piping work package 058 | WBS.02.01 | Piping | Area C | 2025-01-30 | 2025-06-12 | 2025-01-30 | 2025-06-12 | 133 | 1478.2 | 1 | Complete | 2025-09-30
A0059 | Electrical work package 059 | WBS.02.01 | Electrical | Area C | 2025-07-18 | 2025-09-01 | 2025-07-18 |  | 45 | 1721 | 0.9914 | In Progress | 2025-09-30
A0060 | Instrumentation work package 060 | WBS.02.01 | Instrumentation | Area C | 2025-02-23 | 2025-06-13 | 2025-02-23 | 2025-06-13 | 110 | 974.9 | 1 | Complete | 2025-09-30
A0061 | Civil work package 061 | WBS.02.02 | Civil | Area A | 2026-01-17 | 2026-04-05 |  |  | 78 | 310.5 | 0 | Not Started | 2025-09-30
A0062 | Mechanical work package 062 | WBS.02.02 | Mechanical | Area A | 2025-03-05 | 2025-04-05 | 2025-03-05 |  | 31 | 683 | 0.9736 | In Progress | 2025-09-30
A0063 | Piping work package 063 | WBS.02.02 | Piping | Area A | 2025-08-15 | 2025-12-17 | 2025-08-15 |  | 124 | 762.1 | 0.3565 | In Progress | 2025-09-30
A0064 | Electrical work package 064 | WBS.02.02 | Electrical | Area A | 2025-08-05 | 2025-10-13 | 2025-08-05 |  | 69 | 1169.4 | 0.6839 | In Progress | 2025-09-30
A0065 | Instrumentation work package 065 | WBS.02.02 | Instrumentation | Area A | 2026-01-26 | 2026-04-22 |  |  | 86 | 1228.2 | 0 | Not Started | 2025-09-30
A0066 | Civil work package 066 | WBS.02.02 | Civil | Area B | 2025-04-04 | 2025-06-16 | 2025-04-04 |  | 73 | 945.9 | 0.9733 | In Progress | 2025-09-30
A0067 | Mechanical work package 067 | WBS.02.02 | Mechanical | Area B | 2025-12-18 | 2026-04-16 |  |  | 119 | 397.4 | 0 | Not Started | 2025-09-30
A0068 | Piping work package 068 | WBS.02.02 | Piping | Area B | 2025-07-23 | 2025-11-19 | 2025-07-23 |  | 119 | 143.1 | 0.5371 | In Progress | 2025-09-30
A0069 | Electrical work package 069 | WBS.02.02 | Electrical | Area B | 2025-02-21 | 2025-05-15 | 2025-02-21 |  | 83 | 996.1 | 0.96 | In Progress | 2025-09-30
A0070 | Instrumentation work package 070 | WBS.02.02 | Instrumentation | Area B | 2025-02-26 | 2025-07-12 | 2025-02-26 |  | 136 | 1101 | 0.96 | In Progress | 2025-09-30
A0071 | Civil work package 071 | WBS.02.03 | Civil | Area C | 2025-09-15 | 2026-01-12 | 2025-09-15 |  | 119 | 822.5 | 0.1548 | In Progress | 2025-09-30
A0072 | Mechanical work package 072 | WBS.02.03 | Mechanical | Area C | 2025-06-08 | 2025-11-03 | 2025-06-08 |  | 148 | 1121.9 | 0.652 | In Progress | 2025-09-30
A0073 | Piping work package 073 | WBS.02.03 | Piping | Area C | 2025-03-21 | 2025-08-05 | 2025-03-21 |  | 137 | 218 | 0.96 | In Progress | 2025-09-30
A0074 | Electrical work package 074 | WBS.02.03 | Electrical | Area C | 2026-02-26 | 2026-06-30 |  |  | 133 | 1485.4 | 0 | Not Started | 2025-09-30
A0075 | Instrumentation work package 075 | WBS.02.03 | Instrumentation | Area C | 2025-09-08 | 2025-11-10 | 2025-09-08 |  | 63 | 1403.5 | 0.3026 | In Progress | 2025-09-30
A0076 | Civil work package 076 | WBS.02.03 | Civil | Area A | 2025-02-24 | 2025-06-07 | 2025-02-24 |  | 103 | 576.4 | 0.96 | In Progress | 2025-09-30
A0077 | Mechanical work package 077 | WBS.02.03 | Mechanical | Area A | 2025-05-30 | 2025-07-15 | 2025-05-30 | 2025-07-15 | 46 | 189 | 1 | Complete | 2025-09-30
A0078 | Piping work package 078 | WBS.02.03 | Piping | Area A | 2025-11-28 | 2026-03-09 |  |  | 101 | 891.1 | 0 | Not Started | 2025-09-30
A0079 | Electrical work package 079 | WBS.02.03 | Electrical | Area A | 2026-02-13 | 2026-04-05 |  |  | 51 | 194.4 | 0 | Not Started | 2025-09-30
A0080 | Instrumentation work package 080 | WBS.02.03 | Instrumentation | Area A | 2025-04-02 | 2025-05-21 | 2025-04-02 | 2025-05-21 | 49 | 362.5 | 0.9992 | Complete | 2025-09-30
A0081 | Civil work package 081 | WBS.02.04 | Civil | Area B | 2025-06-23 | 2025-10-28 | 2025-06-23 |  | 127 | 835.3 | 0.7487 | In Progress | 2025-09-30
A0082 | Mechanical work package 082 | WBS.02.04 | Mechanical | Area B | 2025-04-15 | 2025-08-30 | 2025-04-15 |  | 137 | 740.3 | 0.9736 | In Progress | 2025-09-30
A0083 | Piping work package 083 | WBS.02.04 | Piping | Area B | 2025-03-06 | 2025-07-09 | 2025-03-06 |  | 125 | 1146.5 | 0.96 | In Progress | 2025-09-30
A0084 | Electrical work package 084 | WBS.02.04 | Electrical | Area B | 2025-04-22 | 2025-08-19 | 2025-04-22 |  | 119 | 137.7 | 0.96 | In Progress | 2025-09-30
A0085 | Instrumentation work package 085 | WBS.02.04 | Instrumentation | Area B | 2025-02-22 | 2025-07-03 | 2025-02-22 |  | 131 | 299.3 | 0.96 | In Progress | 2025-09-30
A0086 | Civil work package 086 | WBS.02.04 | Civil | Area C | 2025-11-11 | 2026-02-25 |  |  | 106 | 1273.6 | 0 | Not Started | 2025-09-30
A0087 | Mechanical work package 087 | WBS.02.04 | Mechanical | Area C | 2025-07-23 | 2025-12-13 | 2025-07-23 |  | 143 | 343.8 | 0.4789 | In Progress | 2025-09-30
A0088 | Piping work package 088 | WBS.02.04 | Piping | Area C | 2025-11-01 | 2026-03-21 |  |  | 140 | 1296.5 | 0 | Not Started | 2025-09-30
A0089 | Electrical work package 089 | WBS.02.04 | Electrical | Area C | 2026-02-11 | 2026-06-30 |  |  | 141 | 855.4 | 0 | Not Started | 2025-09-30
A0090 | Instrumentation work package 090 | WBS.02.04 | Instrumentation | Area C | 2025-01-29 | 2025-04-09 | 2025-01-29 |  | 70 | 1460.9 | 0.96 | In Progress | 2025-09-30
A0091 | Civil work package 091 | WBS.02.05 | Civil | Area A | 2025-06-03 | 2025-08-13 | 2025-06-03 |  | 71 | 1348.5 | 0.96 | In Progress | 2025-09-30
A0092 | Mechanical work package 092 | WBS.02.05 | Mechanical | Area A | 2025-08-08 | 2025-10-27 | 2025-08-08 |  | 80 | 1653.5 | 0.5708 | In Progress | 2025-09-30
A0093 | Piping work package 093 | WBS.02.05 | Piping | Area A | 2025-02-11 | 2025-07-10 | 2025-02-11 |  | 149 | 943.8 | 0.96 | In Progress | 2025-09-30
A0094 | Electrical work package 094 | WBS.02.05 | Electrical | Area A | 2025-04-04 | 2025-05-26 | 2025-04-04 |  | 52 | 142.9 | 0.9662 | In Progress | 2025-09-30
A0095 | Instrumentation work package 095 | WBS.02.05 | Instrumentation | Area A | 2025-08-19 | 2025-11-09 | 2025-08-19 |  | 82 | 769.3 | 0.4665 | In Progress | 2025-09-30
A0096 | Civil work package 096 | WBS.02.05 | Civil | Area B | 2025-10-09 | 2025-12-27 |  |  | 79 | 123.7 | 0 | Not Started | 2025-09-30
A0097 | Mechanical work package 097 | WBS.02.05 | Mechanical | Area B | 2025-01-14 | 2025-02-25 | 2025-01-14 |  | 42 | 1455.9 | 0.96 | In Progress | 2025-09-30
A0098 | Piping work package 098 | WBS.02.05 | Piping | Area B | 2025-11-12 | 2026-03-24 |  |  | 132 | 1508 | 0 | Not Started | 2025-09-30
A0099 | Electrical work package 099 | WBS.02.05 | Electrical | Area B | 2025-01-11 | 2025-02-20 | 2025-01-11 |  | 40 | 437.6 | 0.96 | In Progress | 2025-09-30
A0100 | Instrumentation work package 100 | WBS.02.05 | Instrumentation | Area B | 2025-12-23 | 2026-03-04 |  |  | 71 | 526.2 | 0 | Not Started | 2025-09-30
A0101 | Civil work package 101 | WBS.03.01 | Civil | Area C | 2025-08-31 | 2025-11-21 | 2025-08-31 |  | 82 | 586.5 | 0.4074 | In Progress | 2025-09-30
A0102 | Mechanical work package 102 | WBS.03.01 | Mechanical | Area C | 2026-01-25 | 2026-05-30 |  |  | 125 | 811.4 | 0 | Not Started | 2025-09-30
A0103 | Piping work package 103 | WBS.03.01 | Piping | Area C | 2025-03-06 | 2025-07-14 | 2025-03-06 |  | 130 | 1773.2 | 0.96 | In Progress | 2025-09-30
A0104 | Electrical work package 104 | WBS.03.01 | Electrical | Area C | 2025-05-03 | 2025-08-07 | 2025-05-03 | 2025-08-07 | 96 | 1200.4 | 1 | Complete | 2025-09-30
A0105 | Instrumentation work package 105 | WBS.03.01 | Instrumentation | Area C | 2025-03-22 | 2025-08-08 | 2025-03-22 |  | 139 | 800.3 | 0.96 | In Progress | 2025-09-30
A0106 | Civil work package 106 | WBS.03.01 | Civil | Area A | 2025-02-10 | 2025-05-23 | 2025-02-10 |  | 102 | 502 | 0.96 | In Progress | 2025-09-30
A0107 | Mechanical work package 107 | WBS.03.01 | Mechanical | Area A | 2025-09-06 | 2025-12-02 | 2025-09-06 |  | 87 | 1221.5 | 0.2887 | In Progress | 2025-09-30
A0108 | Piping work package 108 | WBS.03.01 | Piping | Area A | 2025-08-07 | 2025-11-16 | 2025-08-07 |  | 101 | 654.9 | 0.5785 | In Progress | 2025-09-30
A0109 | Electrical work package 109 | WBS.03.01 | Electrical | Area A | 2025-04-21 | 2025-08-27 | 2025-04-21 |  | 128 | 1455 | 0.9736 | In Progress | 2025-09-30
A0110 | Instrumentation work package 110 | WBS.03.01 | Instrumentation | Area A | 2026-02-04 | 2026-03-22 |  |  | 46 | 1714.4 | 0 | Not Started | 2025-09-30
A0111 | Civil work package 111 | WBS.03.02 | Civil | Area B | 2025-12-18 | 2026-04-06 |  |  | 109 | 1270.7 | 0 | Not Started | 2025-09-30
A0112 | Mechanical work package 112 | WBS.03.02 | Mechanical | Area B | 2025-03-24 | 2025-06-30 | 2025-03-24 |  | 98 | 1654.6 | 0.96 | In Progress | 2025-09-30
A0113 | Piping work package 113 | WBS.03.02 | Piping | Area B | 2026-01-11 | 2026-05-22 |  |  | 131 | 628.9 | 0 | Not Started | 2025-09-30
A0114 | Electrical work package 114 | WBS.03.02 | Electrical | Area B | 2025-02-08 | 2025-06-01 | 2025-02-08 |  | 113 | 664.6 | 0.9916 | In Progress | 2025-09-30
A0115 | Instrumentation work package 115 | WBS.03.02 | Instrumentation | Area B | 2025-05-23 | 2025-09-05 | 2025-05-23 | 2025-09-05 | 105 | 1603.9 | 0.9969 | Complete | 2025-09-30
A0116 | Civil work package 116 | WBS.03.02 | Civil | Area C | 2025-07-31 | 2025-11-13 | 2025-07-31 |  | 105 | 1582.7 | 0.5948 | In Progress | 2025-09-30
A0117 | Mechanical work package 117 | WBS.03.02 | Mechanical | Area C | 2025-04-18 | 2025-05-31 | 2025-04-18 |  | 43 | 690 | 0.96 | In Progress | 2025-09-30
A0118 | Piping work package 118 | WBS.03.02 | Piping | Area C | 2025-06-20 | 2025-10-09 | 2025-06-20 |  | 111 | 455.4 | 0.9712 | In Progress | 2025-09-30
A0119 | Electrical work package 119 | WBS.03.02 | Electrical | Area C | 2025-09-26 | 2025-11-15 | 2025-09-26 |  | 50 | 1784.8 | 0.1312 | In Progress | 2025-09-30
A0120 | Instrumentation work package 120 | WBS.03.02 | Instrumentation | Area C | 2025-04-15 | 2025-06-05 | 2025-04-15 |  | 51 | 459.2 | 0.96 | In Progress | 2025-09-30
A0121 | Civil work package 121 | WBS.03.03 | Civil | Area A | 2025-11-01 | 2025-12-19 |  |  | 48 | 1483.2 | 0 | Not Started | 2025-09-30
A0122 | Mechanical work package 122 | WBS.03.03 | Mechanical | Area A | 2025-02-14 | 2025-06-29 | 2025-02-14 |  | 135 | 536.8 | 0.96 | In Progress | 2025-09-30
A0123 | Piping work package 123 | WBS.03.03 | Piping | Area A | 2025-02-12 | 2025-05-02 | 2025-02-12 |  | 79 | 721 | 0.96 | In Progress | 2025-09-30
A0124 | Electrical work package 124 | WBS.03.03 | Electrical | Area A | 2026-01-07 | 2026-04-06 |  |  | 89 | 906.6 | 0 | Not Started | 2025-09-30
A0125 | Instrumentation work package 125 | WBS.03.03 | Instrumentation | Area A | 2025-04-30 | 2025-09-12 | 2025-04-30 | 2025-09-12 | 135 | 1451.6 | 1 | Complete | 2025-09-30
A0126 | Civil work package 126 | WBS.03.03 | Civil | Area B | 2025-09-29 | 2026-01-27 |  |  | 120 | 352.8 | 0 | Not Started | 2025-09-30
A0127 | Mechanical work package 127 | WBS.03.03 | Mechanical | Area B | 2025-03-16 | 2025-07-22 | 2025-03-16 |  | 128 | 1511.3 | 0.96 | In Progress | 2025-09-30
A0128 | Piping work package 128 | WBS.03.03 | Piping | Area B | 2025-10-05 | 2026-01-07 |  |  | 94 | 1421.3 | 0 | Not Started | 2025-09-30
A0129 | Electrical work package 129 | WBS.03.03 | Electrical | Area B | 2025-10-05 | 2026-02-23 |  |  | 141 | 256.3 | 0 | Not Started | 2025-09-30
A0130 | Instrumentation work package 130 | WBS.03.03 | Instrumentation | Area B | 2025-02-03 | 2025-05-13 | 2025-02-03 |  | 99 | 674.9 | 0.9612 | In Progress | 2025-09-30
A0131 | Civil work package 131 | WBS.03.04 | Civil | Area C | 2025-10-26 | 2026-01-17 |  |  | 83 | 550.6 | 0 | Not Started | 2025-09-30
A0132 | Mechanical work package 132 | WBS.03.04 | Mechanical | Area C | 2025-10-31 | 2025-12-26 |  |  | 56 | 221.7 | 0 | Not Started | 2025-09-30
A0133 | Piping work package 133 | WBS.03.04 | Piping | Area C | 2025-07-05 | 2025-10-19 | 2025-07-05 |  | 106 | 763.9 | 0.7336 | In Progress | 2025-09-30
A0134 | Electrical work package 134 | WBS.03.04 | Electrical | Area C | 2025-04-07 | 2025-05-10 | 2025-04-07 |  | 33 | 1200.9 | 0.96 | In Progress | 2025-09-30
A0135 | Instrumentation work package 135 | WBS.03.04 | Instrumentation | Area C | 2025-12-03 | 2026-04-13 |  |  | 131 | 1389 | 0 | Not Started | 2025-09-30
A0136 | Civil work package 136 | WBS.03.04 | Civil | Area A | 2025-02-25 | 2025-04-11 | 2025-02-25 |  | 45 | 1259.2 | 0.96 | In Progress | 2025-09-30
A0137 | Mechanical work package 137 | WBS.03.04 | Mechanical | Area A | 2025-05-01 | 2025-09-03 | 2025-05-01 |  | 125 | 613.8 | 0.96 | In Progress | 2025-09-30
A0138 | Piping work package 138 | WBS.03.04 | Piping | Area A | 2025-10-31 | 2026-03-13 |  |  | 133 | 1421.3 | 0 | Not Started | 2025-09-30
A0139 | Electrical work package 139 | WBS.03.04 | Electrical | Area A | 2025-09-28 | 2026-01-20 |  |  | 114 | 1042.6 | 0 | Not Started | 2025-09-30
A0140 | Instrumentation work package 140 | WBS.03.04 | Instrumentation | Area A | 2025-01-20 | 2025-02-28 | 2025-01-20 |  | 39 | 762.7 | 0.96 | In Progress | 2025-09-30
A0141 | Civil work package 141 | WBS.03.05 | Civil | Area B | 2025-03-19 | 2025-04-30 | 2025-03-19 |  | 42 | 1174.7 | 0.9923 | In Progress | 2025-09-30
A0142 | Mechanical work package 142 | WBS.03.05 | Mechanical | Area B | 2025-11-09 | 2026-03-15 |  |  | 126 | 663.9 | 0 | Not Started | 2025-09-30
A0143 | Piping work package 143 | WBS.03.05 | Piping | Area B | 2025-08-20 | 2025-12-15 | 2025-08-20 |  | 117 | 220.4 | 0.3028 | In Progress | 2025-09-30
A0144 | Electrical work package 144 | WBS.03.05 | Electrical | Area B | 2026-03-01 | 2026-05-10 |  |  | 70 | 393.2 | 0 | Not Started | 2025-09-30
A0145 | Instrumentation work package 145 | WBS.03.05 | Instrumentation | Area B | 2025-04-14 | 2025-09-10 | 2025-04-14 |  | 149 | 1756.6 | 0.96 | In Progress | 2025-09-30
A0146 | Civil work package 146 | WBS.03.05 | Civil | Area C | 2026-01-14 | 2026-05-11 |  |  | 117 | 1357.5 | 0 | Not Started | 2025-09-30
A0147 | Mechanical work package 147 | WBS.03.05 | Mechanical | Area C | 2025-07-13 | 2025-11-07 | 2025-07-13 |  | 117 | 917.1 | 0.6499 | In Progress | 2025-09-30
A0148 | Piping work package 148 | WBS.03.05 | Piping | Area C | 2026-02-02 | 2026-03-29 |  |  | 55 | 1151.5 | 0 | Not Started | 2025-09-30
A0149 | Electrical work package 149 | WBS.03.05 | Electrical | Area C | 2025-03-24 | 2025-05-21 | 2025-03-24 |  | 58 | 1750.8 | 0.96 | In Progress | 2025-09-30
A0150 | Instrumentation work package 150 | WBS.03.05 | Instrumentation | Area C | 2025-07-16 | 2025-10-15 | 2025-07-16 |  | 91 | 697.9 | 0.8278 | In Progress | 2025-09-30
A0151 | Civil work package 151 | WBS.04.01 | Civil | Area A | 2025-12-04 | 2026-01-18 |  |  | 45 | 1748.1 | 0 | Not Started | 2025-09-30
A0152 | Mechanical work package 152 | WBS.04.01 | Mechanical | Area A | 2025-07-10 | 2025-09-07 | 2025-07-10 | 2025-09-07 | 59 | 1141.5 | 1 | Complete | 2025-09-30
A0153 | Piping work package 153 | WBS.04.01 | Piping | Area A | 2026-01-03 | 2026-05-09 |  |  | 126 | 1086.8 | 0 | Not Started | 2025-09-30
A0154 | Electrical work package 154 | WBS.04.01 | Electrical | Area A | 2025-08-22 | 2026-01-11 | 2025-08-22 |  | 142 | 147.7 | 0.183 | In Progress | 2025-09-30
A0155 | Instrumentation work package 155 | WBS.04.01 | Instrumentation | Area A | 2025-01-23 | 2025-03-11 | 2025-01-23 |  | 47 | 1777 | 0.9696 | In Progress | 2025-09-30
A0156 | Civil work package 156 | WBS.04.01 | Civil | Area B | 2025-08-04 | 2025-11-22 | 2025-08-04 |  | 110 | 320.2 | 0.4021 | In Progress | 2025-09-30
A0157 | Mechanical work package 157 | WBS.04.01 | Mechanical | Area B | 2026-02-27 | 2026-04-09 |  |  | 41 | 1236.9 | 0 | Not Started | 2025-09-30
A0158 | Piping work package 158 | WBS.04.01 | Piping | Area B | 2026-02-16 | 2026-06-07 |  |  | 111 | 935.1 | 0 | Not Started | 2025-09-30
A0159 | Electrical work package 159 | WBS.04.01 | Electrical | Area B | 2025-04-08 | 2025-07-26 | 2025-04-08 |  | 109 | 757.4 | 0.978 | In Progress | 2025-09-30
A0160 | Instrumentation work package 160 | WBS.04.01 | Instrumentation | Area B | 2026-01-15 | 2026-05-18 |  |  | 123 | 1055.3 | 0 | Not Started | 2025-09-30
A0161 | Civil work package 161 | WBS.04.02 | Civil | Area C | 2025-12-19 | 2026-04-19 |  |  | 121 | 1452.2 | 0 | Not Started | 2025-09-30
A0162 | Mechanical work package 162 | WBS.04.02 | Mechanical | Area C | 2025-05-25 | 2025-08-06 | 2025-05-25 |  | 73 | 761.4 | 0.96 | In Progress | 2025-09-30
A0163 | Piping work package 163 | WBS.04.02 | Piping | Area C | 2025-04-13 | 2025-05-21 | 2025-04-13 |  | 38 | 1117.9 | 0.9656 | In Progress | 2025-09-30
A0164 | Electrical work package 164 | WBS.04.02 | Electrical | Area C | 2025-08-17 | 2025-11-12 | 2025-08-17 |  | 87 | 124.1 | 0.5154 | In Progress | 2025-09-30
A0165 | Instrumentation work package 165 | WBS.04.02 | Instrumentation | Area C | 2025-09-24 | 2026-01-23 | 2025-09-24 |  | 121 | 1478.3 | 0.0473 | In Progress | 2025-09-30
A0166 | Civil work package 166 | WBS.04.02 | Civil | Area A | 2025-01-31 | 2025-06-22 | 2025-01-31 |  | 142 | 684.8 | 0.96 | In Progress | 2025-09-30
A0167 | Mechanical work package 167 | WBS.04.02 | Mechanical | Area A | 2025-12-17 | 2026-03-21 |  |  | 94 | 615.4 | 0 | Not Started | 2025-09-30
A0168 | Piping work package 168 | WBS.04.02 | Piping | Area A | 2025-03-24 | 2025-07-13 | 2025-03-24 |  | 111 | 392.1 | 0.96 | In Progress | 2025-09-30
A0169 | Electrical work package 169 | WBS.04.02 | Electrical | Area A | 2026-02-24 | 2026-05-23 |  |  | 88 | 1466.3 | 0 | Not Started | 2025-09-30
A0170 | Instrumentation work package 170 | WBS.04.02 | Instrumentation | Area A | 2025-12-24 | 2026-05-09 |  |  | 136 | 472.3 | 0 | Not Started | 2025-09-30
A0171 | Civil work package 171 | WBS.04.03 | Civil | Area B | 2025-12-07 | 2026-02-07 |  |  | 62 | 1494.9 | 0 | Not Started | 2025-09-30
A0172 | Mechanical work package 172 | WBS.04.03 | Mechanical | Area B | 2025-09-15 | 2025-11-04 | 2025-09-15 |  | 50 | 1347.4 | 0.3019 | In Progress | 2025-09-30
A0173 | Piping work package 173 | WBS.04.03 | Piping | Area B | 2025-09-24 | 2025-12-28 | 2025-09-24 |  | 95 | 478.9 | 0.0984 | In Progress | 2025-09-30
A0174 | Electrical work package 174 | WBS.04.03 | Electrical | Area B | 2025-07-09 | 2025-11-02 | 2025-07-09 |  | 116 | 1271 | 0.7448 | In Progress | 2025-09-30
A0175 | Instrumentation work package 175 | WBS.04.03 | Instrumentation | Area B | 2025-02-11 | 2025-06-28 | 2025-02-11 |  | 137 | 410 | 0.96 | In Progress | 2025-09-30
A0176 | Civil work package 176 | WBS.04.03 | Civil | Area C | 2025-02-04 | 2025-06-10 | 2025-02-04 |  | 126 | 482 | 0.96 | In Progress | 2025-09-30
A0177 | Mechanical work package 177 | WBS.04.03 | Mechanical | Area C | 2025-05-29 | 2025-09-16 | 2025-05-29 |  | 110 | 1789.9 | 0.9708 | In Progress | 2025-09-30
A0178 | Piping work package 178 | WBS.04.03 | Piping | Area C | 2025-09-04 | 2026-01-26 | 2025-09-04 |  | 144 | 381.5 | 0.1541 | In Progress | 2025-09-30
A0179 | Electrical work package 179 | WBS.04.03 | Electrical | Area C | 2025-11-27 | 2026-02-06 |  |  | 71 | 1223.6 | 0 | Not Started | 2025-09-30
A0180 | Instrumentation work package 180 | WBS.04.03 | Instrumentation | Area C | 2025-08-18 | 2025-11-30 | 2025-08-18 |  | 104 | 233.3 | 0.4348 | In Progress | 2025-09-30
A0181 | Civil work package 181 | WBS.04.04 | Civil | Area A | 2025-01-21 | 2025-03-28 | 2025-01-21 |  | 66 | 532.6 | 0.96 | In Progress | 2025-09-30
A0182 | Mechanical work package 182 | WBS.04.04 | Mechanical | Area A | 2025-09-21 | 2025-12-21 | 2025-09-21 |  | 91 | 1661.4 | 0.0851 | In Progress | 2025-09-30
A0183 | Piping work package 183 | WBS.04.04 | Piping | Area A | 2026-01-14 | 2026-05-20 |  |  | 126 | 1438.9 | 0 | Not Started | 2025-09-30
A0184 | Electrical work package 184 | WBS.04.04 | Electrical | Area A | 2025-06-03 | 2025-10-28 | 2025-06-03 |  | 147 | 1182.5 | 0.8309 | In Progress | 2025-09-30
A0185 | Instrumentation work package 185 | WBS.04.04 | Instrumentation | Area A | 2025-03-22 | 2025-06-20 | 2025-03-22 |  | 90 | 765.7 | 0.96 | In Progress | 2025-09-30
A0186 | Civil work package 186 | WBS.04.04 | Civil | Area B | 2026-02-25 | 2026-05-17 |  |  | 81 | 616.3 | 0 | Not Started | 2025-09-30
A0187 | Mechanical work package 187 | WBS.04.04 | Mechanical | Area B | 2025-09-29 | 2026-01-15 |  |  | 108 | 341.5 | 0 | Not Started | 2025-09-30
A0188 | Piping work package 188 | WBS.04.04 | Piping | Area B | 2026-03-04 | 2026-05-01 |  |  | 58 | 324.7 | 0 | Not Started | 2025-09-30
A0189 | Electrical work package 189 | WBS.04.04 | Electrical | Area B | 2025-08-13 | 2026-01-09 | 2025-08-13 |  | 149 | 1480 | 0.3331 | In Progress | 2025-09-30
A0190 | Instrumentation work package 190 | WBS.04.04 | Instrumentation | Area B | 2025-03-03 | 2025-07-17 | 2025-03-03 |  | 136 | 853.6 | 0.96 | In Progress | 2025-09-30
A0191 | Civil work package 191 | WBS.04.05 | Civil | Area C | 2025-12-02 | 2026-01-02 |  |  | 31 | 795.8 | 0 | Not Started | 2025-09-30
A0192 | Mechanical work package 192 | WBS.04.05 | Mechanical | Area C | 2025-01-11 | 2025-03-10 | 2025-01-11 |  | 58 | 1758.5 | 0.98 | In Progress | 2025-09-30
A0193 | Piping work package 193 | WBS.04.05 | Piping | Area C | 2025-07-20 | 2025-11-28 | 2025-07-20 |  | 131 | 248.7 | 0.5552 | In Progress | 2025-09-30
A0194 | Electrical work package 194 | WBS.04.05 | Electrical | Area C | 2025-06-16 | 2025-09-01 | 2025-06-16 | 2025-09-01 | 77 | 870.2 | 1 | Complete | 2025-09-30
A0195 | Instrumentation work package 195 | WBS.04.05 | Instrumentation | Area C | 2025-04-25 | 2025-09-02 | 2025-04-25 | 2025-09-02 | 130 | 146.1 | 1 | Complete | 2025-09-30
A0196 | Civil work package 196 | WBS.04.05 | Civil | Area A | 2025-10-06 | 2026-01-17 |  |  | 103 | 194.6 | 0 | Not Started | 2025-09-30
A0197 | Mechanical work package 197 | WBS.04.05 | Mechanical | Area A | 2025-01-23 | 2025-03-04 | 2025-01-23 |  | 40 | 1312.1 | 0.96 | In Progress | 2025-09-30
A0198 | Piping work package 198 | WBS.04.05 | Piping | Area A | 2025-10-17 | 2025-12-08 |  |  | 52 | 379.5 | 0 | Not Started | 2025-09-30
A0199 | Electrical work package 199 | WBS.04.05 | Electrical | Area A | 2025-10-01 | 2025-12-15 |  |  | 75 | 433.8 | 0 | Not Started | 2025-09-30
A0200 | Instrumentation work package 200 | WBS.04.05 | Instrumentation | Area A | 2025-01-24 | 2025-06-19 | 2025-01-24 |  | 146 | 1453.8 | 0.96 | In Progress | 2025-09-30
A0201 | Civil work package 201 | WBS.05.01 | Civil | Area B | 2025-12-21 | 2026-04-08 |  |  | 108 | 300.3 | 0 | Not Started | 2025-09-30
A0202 | Mechanical work package 202 | WBS.05.01 | Mechanical | Area B | 2026-02-15 | 2026-04-14 |  |  | 58 | 289 | 0 | Not Started | 2025-09-30
A0203 | Piping work package 203 | WBS.05.01 | Piping | Area B | 2026-01-11 | 2026-05-22 |  |  | 131 | 1660.6 | 0 | Not Started | 2025-09-30
A0204 | Electrical work package 204 | WBS.05.01 | Electrical | Area B | 2025-12-05 | 2026-03-23 |  |  | 108 | 385.2 | 0 | Not Started | 2025-09-30
A0205 | Instrumentation work package 205 | WBS.05.01 | Instrumentation | Area B | 2025-08-11 | 2025-12-19 | 2025-08-11 |  | 130 | 1340.4 | 0.3193 | In Progress | 2025-09-30
A0206 | Civil work package 206 | WBS.05.01 | Civil | Area C | 2025-10-29 | 2026-03-12 |  |  | 134 | 1174.4 | 0 | Not Started | 2025-09-30
A0207 | Mechanical work package 207 | WBS.05.01 | Mechanical | Area C | 2025-12-16 | 2026-02-08 |  |  | 54 | 1034.7 | 0 | Not Started | 2025-09-30
A0208 | Piping work package 208 | WBS.05.01 | Piping | Area C | 2025-09-01 | 2025-10-01 | 2025-09-01 |  | 30 | 1388.9 | 0.811 | In Progress | 2025-09-30
A0209 | Electrical work package 209 | WBS.05.01 | Electrical | Area C | 2025-05-26 | 2025-07-12 | 2025-05-26 | 2025-07-12 | 47 | 605.6 | 1 | Complete | 2025-09-30
A0210 | Instrumentation work package 210 | WBS.05.01 | Instrumentation | Area C | 2025-06-23 | 2025-09-10 | 2025-06-23 |  | 79 | 1276.5 | 0.96 | In Progress | 2025-09-30
A0211 | Civil work package 211 | WBS.05.02 | Civil | Area A | 2025-10-09 | 2025-11-15 |  |  | 37 | 1077.6 | 0 | Not Started | 2025-09-30
A0212 | Mechanical work package 212 | WBS.05.02 | Mechanical | Area A | 2025-05-02 | 2025-09-08 | 2025-05-02 |  | 129 | 937 | 0.96 | In Progress | 2025-09-30
A0213 | Piping work package 213 | WBS.05.02 | Piping | Area A | 2025-12-11 | 2026-03-13 |  |  | 92 | 837.1 | 0 | Not Started | 2025-09-30
A0214 | Electrical work package 214 | WBS.05.02 | Electrical | Area A | 2025-09-20 | 2026-01-16 | 2025-09-20 |  | 118 | 1797.2 | 0.1022 | In Progress | 2025-09-30
A0215 | Instrumentation work package 215 | WBS.05.02 | Instrumentation | Area A | 2025-02-25 | 2025-05-15 | 2025-02-25 |  | 79 | 1524.5 | 0.96 | In Progress | 2025-09-30
A0216 | Civil work package 216 | WBS.05.02 | Civil | Area B | 2025-05-29 | 2025-07-01 | 2025-05-29 | 2025-07-01 | 33 | 121.6 | 1 | Complete | 2025-09-30
A0217 | Mechanical work package 217 | WBS.05.02 | Mechanical | Area B | 2025-04-27 | 2025-07-17 | 2025-04-27 |  | 81 | 1581.1 | 0.96 | In Progress | 2025-09-30
A0218 | Piping work package 218 | WBS.05.02 | Piping | Area B | 2025-03-04 | 2025-04-12 | 2025-03-04 |  | 39 | 1332.1 | 0.96 | In Progress | 2025-09-30
A0219 | Electrical work package 219 | WBS.05.02 | Electrical | Area B | 2025-09-25 | 2025-11-10 | 2025-09-25 |  | 46 | 1372.4 | 0.0849 | In Progress | 2025-09-30
A0220 | Instrumentation work package 220 | WBS.05.02 | Instrumentation | Area B | 2026-01-30 | 2026-03-30 |  |  | 59 | 547.8 | 0 | Not Started | 2025-09-30
A0221 | Civil work package 221 | WBS.05.03 | Civil | Area C | 2025-01-20 | 2025-02-26 | 2025-01-20 |  | 37 | 1639.1 | 0.96 | In Progress | 2025-09-30
A0222 | Mechanical work package 222 | WBS.05.03 | Mechanical | Area C | 2025-01-15 | 2025-05-04 | 2025-01-15 |  | 109 | 1737 | 0.96 | In Progress | 2025-09-30
A0223 | Piping work package 223 | WBS.05.03 | Piping | Area C | 2025-04-01 | 2025-07-07 | 2025-04-01 | 2025-07-07 | 97 | 878 | 1 | Complete | 2025-09-30
A0224 | Electrical work package 224 | WBS.05.03 | Electrical | Area C | 2026-01-06 | 2026-04-13 |  |  | 97 | 980.2 | 0 | Not Started | 2025-09-30
A0225 | Instrumentation work package 225 | WBS.05.03 | Instrumentation | Area C | 2025-08-27 | 2025-10-05 | 2025-08-27 |  | 39 | 868.3 | 0.7868 | In Progress | 2025-09-30
A0226 | Civil work package 226 | WBS.05.03 | Civil | Area A | 2025-10-12 | 2026-01-15 |  |  | 95 | 187.1 | 0 | Not Started | 2025-09-30
A0227 | Mechanical work package 227 | WBS.05.03 | Mechanical | Area A | 2025-03-17 | 2025-05-25 | 2025-03-17 |  | 69 | 1381.6 | 0.96 | In Progress | 2025-09-30
A0228 | Piping work package 228 | WBS.05.03 | Piping | Area A | 2026-03-05 | 2026-06-30 |  |  | 122 | 126.7 | 0 | Not Started | 2025-09-30
A0229 | Electrical work package 229 | WBS.05.03 | Electrical | Area A | 2025-02-20 | 2025-06-08 | 2025-02-20 |  | 108 | 1494 | 0.96 | In Progress | 2025-09-30
A0230 | Instrumentation work package 230 | WBS.05.03 | Instrumentation | Area A | 2025-09-11 | 2025-12-26 | 2025-09-11 |  | 106 | 1452.4 | 0.1421 | In Progress | 2025-09-30
A0231 | Civil work package 231 | WBS.05.04 | Civil | Area B | 2025-12-13 | 2026-02-19 |  |  | 68 | 1554.3 | 0 | Not Started | 2025-09-30
A0232 | Mechanical work package 232 | WBS.05.04 | Mechanical | Area B | 2025-07-14 | 2025-10-25 | 2025-07-14 |  | 103 | 223.6 | 0.786 | In Progress | 2025-09-30
A0233 | Piping work package 233 | WBS.05.04 | Piping | Area B | 2026-03-05 | 2026-06-23 |  |  | 110 | 1171.6 | 0 | Not Started | 2025-09-30
A0234 | Electrical work package 234 | WBS.05.04 | Electrical | Area B | 2025-11-11 | 2026-03-27 |  |  | 136 | 216.6 | 0 | Not Started | 2025-09-30
A0235 | Instrumentation work package 235 | WBS.05.04 | Instrumentation | Area B | 2025-11-07 | 2026-01-13 |  |  | 67 | 890.4 | 0 | Not Started | 2025-09-30
A0236 | Civil work package 236 | WBS.05.04 | Civil | Area C | 2025-05-30 | 2025-07-19 | 2025-05-30 |  | 50 | 1304.7 | 0.9869 | In Progress | 2025-09-30
A0237 | Mechanical work package 237 | WBS.05.04 | Mechanical | Area C | 2025-07-18 | 2025-11-14 | 2025-07-18 |  | 119 | 1200 | 0.5981 | In Progress | 2025-09-30
A0238 | Piping work package 238 | WBS.05.04 | Piping | Area C | 2025-10-05 | 2025-11-19 |  |  | 45 | 1243 | 0 | Not Started | 2025-09-30
A0239 | Electrical work package 239 | WBS.05.04 | Electrical | Area C | 2025-04-13 | 2025-08-21 | 2025-04-13 |  | 130 | 560.4 | 0.96 | In Progress | 2025-09-30
A0240 | Instrumentation work package 240 | WBS.05.04 | Instrumentation | Area C | 2025-01-20 | 2025-03-27 | 2025-01-20 | 2025-03-27 | 66 | 1203.4 | 1 | Complete | 2025-09-30
A0241 | Civil work package 241 | WBS.05.05 | Civil | Area A | 2025-04-27 | 2025-09-12 | 2025-04-27 |  | 138 | 1233.7 | 0.96 | In Progress | 2025-09-30
A0242 | Mechanical work package 242 | WBS.05.05 | Mechanical | Area A | 2025-08-29 | 2025-11-12 | 2025-08-29 |  | 75 | 1760.1 | 0.3655 | In Progress | 2025-09-30
A0243 | Piping work package 243 | WBS.05.05 | Piping | Area A | 2025-05-06 | 2025-09-16 | 2025-05-06 | 2025-09-16 | 133 | 582.6 | 1 | Complete | 2025-09-30
A0244 | Electrical work package 244 | WBS.05.05 | Electrical | Area A | 2025-12-28 | 2026-03-01 |  |  | 63 | 1581.1 | 0 | Not Started | 2025-09-30
A0245 | Instrumentation work package 245 | WBS.05.05 | Instrumentation | Area A | 2025-01-11 | 2025-04-07 | 2025-01-11 | 2025-04-07 | 86 | 598.2 | 1 | Complete | 2025-09-30
A0246 | Civil work package 246 | WBS.05.05 | Civil | Area B | 2026-01-24 | 2026-03-17 |  |  | 52 | 215.8 | 0 | Not Started | 2025-09-30
A0247 | Mechanical work package 247 | WBS.05.05 | Mechanical | Area B | 2025-02-15 | 2025-07-04 | 2025-02-15 | 2025-07-04 | 139 | 1231 | 1 | Complete | 2025-09-30
A0248 | Piping work package 248 | WBS.05.05 | Piping | Area B | 2025-05-22 | 2025-08-12 | 2025-05-22 |  | 82 | 1411.1 | 0.9913 | In Progress | 2025-09-30
A0249 | Electrical work package 249 | WBS.05.05 | Electrical | Area B | 2025-09-17 | 2026-01-09 | 2025-09-17 |  | 114 | 488.4 | 0.1025 | In Progress | 2025-09-30
A0250 | Instrumentation work package 250 | WBS.05.05 | Instrumentation | Area B | 2026-02-18 | 2026-05-31 |  |  | 102 | 1359 | 0 | Not Started | 2025-09-30
A0251 | Civil work package 251 | WBS.06.01 | Civil | Area C | 2025-07-28 | 2025-09-01 | 2025-07-28 |  | 35 | 320.8 | 0.96 | In Progress | 2025-09-30
A0252 | Mechanical work package 252 | WBS.06.01 | Mechanical | Area C | 2025-04-05 | 2025-07-05 | 2025-04-05 |  | 91 | 89.5 | 0.96 | In Progress | 2025-09-30
A0253 | Piping work package 253 | WBS.06.01 | Piping | Area C | 2025-08-14 | 2025-10-18 | 2025-08-14 |  | 65 | 1682.6 | 0.639 | In Progress | 2025-09-30
A0254 | Electrical work package 254 | WBS.06.01 | Electrical | Area C | 2025-08-12 | 2025-12-24 | 2025-08-12 |  | 134 | 928.9 | 0.3193 | In Progress | 2025-09-30
A0255 | Instrumentation work package 255 | WBS.06.01 | Instrumentation | Area C | 2026-01-31 | 2026-05-26 |  |  | 115 | 1125.6 | 0 | Not Started | 2025-09-30
A0256 | Civil work package 256 | WBS.06.01 | Civil | Area A | 2025-02-24 | 2025-05-11 | 2025-02-24 |  | 76 | 864.7 | 0.96 | In Progress | 2025-09-30
A0257 | Mechanical work package 257 | WBS.06.01 | Mechanical | Area A | 2025-02-09 | 2025-04-22 | 2025-02-09 |  | 72 | 1699.8 | 0.9742 | In Progress | 2025-09-30
A0258 | Piping work package 258 | WBS.06.01 | Piping | Area A | 2025-10-06 | 2026-02-22 |  |  | 139 | 1133.6 | 0 | Not Started | 2025-09-30
A0259 | Electrical work package 259 | WBS.06.01 | Electrical | Area A | 2025-01-11 | 2025-04-01 | 2025-01-11 |  | 80 | 587.5 | 0.96 | In Progress | 2025-09-30
A0260 | Instrumentation work package 260 | WBS.06.01 | Instrumentation | Area A | 2025-06-02 | 2025-09-27 | 2025-06-02 | 2025-09-27 | 117 | 1201.9 | 1 | Complete | 2025-09-30
A0261 | Civil work package 261 | WBS.06.02 | Civil | Area B | 2025-05-17 | 2025-09-18 | 2025-05-17 | 2025-09-18 | 124 | 847.8 | 1 | Complete | 2025-09-30
A0262 | Mechanical work package 262 | WBS.06.02 | Mechanical | Area B | 2025-05-23 | 2025-08-30 | 2025-05-23 |  | 99 | 718.4 | 0.96 | In Progress | 2025-09-30
A0263 | Piping work package 263 | WBS.06.02 | Piping | Area B | 2025-07-10 | 2025-08-26 | 2025-07-10 |  | 47 | 1611 | 0.96 | In Progress | 2025-09-30
A0264 | Electrical work package 264 | WBS.06.02 | Electrical | Area B | 2025-07-01 | 2025-09-06 | 2025-07-01 |  | 67 | 1244.6 | 0.9663 | In Progress | 2025-09-30
A0265 | Instrumentation work package 265 | WBS.06.02 | Instrumentation | Area B | 2025-10-28 | 2025-12-13 |  |  | 46 | 915.2 | 0 | Not Started | 2025-09-30
A0266 | Civil work package 266 | WBS.06.02 | Civil | Area C | 2025-01-19 | 2025-04-05 | 2025-01-19 |  | 76 | 355.2 | 0.96 | In Progress | 2025-09-30
A0267 | Mechanical work package 267 | WBS.06.02 | Mechanical | Area C | 2025-02-24 | 2025-07-18 | 2025-02-24 | 2025-07-18 | 144 | 620 | 1 | Complete | 2025-09-30
A0268 | Piping work package 268 | WBS.06.02 | Piping | Area C | 2025-06-20 | 2025-08-29 | 2025-06-20 |  | 70 | 1011.2 | 0.96 | In Progress | 2025-09-30
A0269 | Electrical work package 269 | WBS.06.02 | Electrical | Area C | 2025-07-14 | 2025-09-18 | 2025-07-14 |  | 66 | 526.1 | 0.96 | In Progress | 2025-09-30
A0270 | Instrumentation work package 270 | WBS.06.02 | Instrumentation | Area C | 2025-09-12 | 2025-10-28 | 2025-09-12 |  | 46 | 843.8 | 0.4262 | In Progress | 2025-09-30
A0271 | Civil work package 271 | WBS.06.03 | Civil | Area A | 2025-09-29 | 2025-11-22 | 2025-09-29 |  | 54 | 759.6 | 0.027 | In Progress | 2025-09-30
A0272 | Mechanical work package 272 | WBS.06.03 | Mechanical | Area A | 2025-08-23 | 2026-01-04 | 2025-08-23 |  | 134 | 304.7 | 0.2749 | In Progress | 2025-09-30
A0273 | Piping work package 273 | WBS.06.03 | Piping | Area A | 2026-02-15 | 2026-04-03 |  |  | 47 | 875.8 | 0 | Not Started | 2025-09-30
A0274 | Electrical work package 274 | WBS.06.03 | Electrical | Area A | 2025-05-08 | 2025-07-01 | 2025-05-08 |  | 54 | 1390.3 | 0.96 | In Progress | 2025-09-30
A0275 | Instrumentation work package 275 | WBS.06.03 | Instrumentation | Area A | 2026-03-03 | 2026-05-20 |  |  | 78 | 1503.3 | 0 | Not Started | 2025-09-30
A0276 | Civil work package 276 | WBS.06.03 | Civil | Area B | 2026-01-08 | 2026-03-31 |  |  | 82 | 1536.8 | 0 | Not Started | 2025-09-30
A0277 | Mechanical work package 277 | WBS.06.03 | Mechanical | Area B | 2025-01-14 | 2025-04-11 | 2025-01-14 |  | 87 | 1262.9 | 0.96 | In Progress | 2025-09-30
A0278 | Piping work package 278 | WBS.06.03 | Piping | Area B | 2025-12-17 | 2026-02-18 |  |  | 63 | 442.4 | 0 | Not Started | 2025-09-30
A0279 | Electrical work package 279 | WBS.06.03 | Electrical | Area B | 2025-11-20 | 2026-01-06 |  |  | 47 | 1375.9 | 0 | Not Started | 2025-09-30
A0280 | Instrumentation work package 280 | WBS.06.03 | Instrumentation | Area B | 2025-02-13 | 2025-05-12 | 2025-02-13 |  | 88 | 213.6 | 0.96 | In Progress | 2025-09-30
A0281 | Civil work package 281 | WBS.06.04 | Civil | Area C | 2025-12-19 | 2026-05-11 |  |  | 143 | 204.4 | 0 | Not Started | 2025-09-30
A0282 | Mechanical work package 282 | WBS.06.04 | Mechanical | Area C | 2025-12-13 | 2026-04-06 |  |  | 114 | 166.4 | 0 | Not Started | 2025-09-30
A0283 | Piping work package 283 | WBS.06.04 | Piping | Area C | 2025-12-17 | 2026-05-07 |  |  | 141 | 776.8 | 0 | Not Started | 2025-09-30
A0284 | Electrical work package 284 | WBS.06.04 | Electrical | Area C | 2026-03-02 | 2026-06-12 |  |  | 102 | 695.4 | 0 | Not Started | 2025-09-30
A0285 | Instrumentation work package 285 | WBS.06.04 | Instrumentation | Area C | 2025-02-05 | 2025-05-27 | 2025-02-05 | 2025-05-27 | 111 | 496.1 | 1 | Complete | 2025-09-30
A0286 | Civil work package 286 | WBS.06.04 | Civil | Area A | 2025-03-08 | 2025-07-09 | 2025-03-08 |  | 123 | 546.8 | 0.96 | In Progress | 2025-09-30
A0287 | Mechanical work package 287 | WBS.06.04 | Mechanical | Area A | 2025-11-23 | 2026-01-30 |  |  | 68 | 80.2 | 0 | Not Started | 2025-09-30
A0288 | Piping work package 288 | WBS.06.04 | Piping | Area A | 2025-05-21 | 2025-07-02 | 2025-05-21 |  | 42 | 699.6 | 0.96 | In Progress | 2025-09-30
A0289 | Electrical work package 289 | WBS.06.04 | Electrical | Area A | 2025-07-11 | 2025-11-27 | 2025-07-11 |  | 139 | 729 | 0.6037 | In Progress | 2025-09-30
A0290 | Instrumentation work package 290 | WBS.06.04 | Instrumentation | Area A | 2025-10-05 | 2026-01-27 |  |  | 114 | 87.5 | 0 | Not Started | 2025-09-30
A0291 | Civil work package 291 | WBS.06.05 | Civil | Area B | 2025-05-14 | 2025-06-25 | 2025-05-14 |  | 42 | 1424.7 | 0.9832 | In Progress | 2025-09-30
A0292 | Mechanical work package 292 | WBS.06.05 | Mechanical | Area B | 2025-07-11 | 2025-10-03 | 2025-07-11 |  | 84 | 439.3 | 0.9088 | In Progress | 2025-09-30
A0293 | Piping work package 293 | WBS.06.05 | Piping | Area B | 2025-12-25 | 2026-05-06 |  |  | 132 | 444.6 | 0 | Not Started | 2025-09-30
A0294 | Electrical work package 294 | WBS.06.05 | Electrical | Area B | 2025-09-24 | 2025-11-28 | 2025-09-24 |  | 65 | 315 | 0.1306 | In Progress | 2025-09-30
A0295 | Instrumentation work package 295 | WBS.06.05 | Instrumentation | Area B | 2025-11-08 | 2025-12-31 |  |  | 53 | 1611.2 | 0 | Not Started | 2025-09-30
A0296 | Civil work package 296 | WBS.06.05 | Civil | Area C | 2025-05-01 | 2025-09-08 | 2025-05-01 |  | 130 | 105.3 | 0.96 | In Progress | 2025-09-30
A0297 | Mechanical work package 297 | WBS.06.05 | Mechanical | Area C | 2025-08-22 | 2025-12-01 | 2025-08-22 |  | 101 | 97.1 | 0.3857 | In Progress | 2025-09-30
A0298 | Piping work package 298 | WBS.06.05 | Piping | Area C | 2025-12-04 | 2026-04-05 |  |  | 122 | 976.6 | 0 | Not Started | 2025-09-30
A0299 | Electrical work package 299 | WBS.06.05 | Electrical | Area C | 2025-01-13 | 2025-03-19 | 2025-01-13 |  | 65 | 1409.8 | 0.96 | In Progress | 2025-09-30
A0300 | Instrumentation work package 300 | WBS.06.05 | Instrumentation | Area C | 2026-01-05 | 2026-02-06 |  |  | 32 | 1625.5 | 0 | Not Started | 2025-09-30

## Contrôles
Control | Issue Count | Status | Action
Physical % > 100 | 1 | REVIEW | bloquer la publication et borner après correction
Completed without Finish | 1 | REVIEW | compléter la date de fin ou repasser en In Progress
BL Finish before BL Start | 1 | REVIEW | corriger les dates dans P6
Missing Discipline | 1 | REVIEW | renseigner la discipline ou affecter Unassigned
Duplicate Activity ID | 1 | REVIEW | dédupliquer avant chargement
Missing Data Date | 0 | PASS | rejeter un snapshot sans Data Date

## Données propres
Activity ID | Activity Name | WBS Code | Discipline | Area | BL Start | BL Finish | Start | Finish | Planned Duration | Budgeted Labor Units | Physical % Complete | Activity Status | Data Date
A0001 | Civil work package 001 | WBS.01.01 | Civil | Area A | 2025-06-16 | 2025-11-07 | 2025-06-16 |  | 144 | 1339 | 1 | In Progress | 2025-09-30
A0002 | Mechanical work package 002 | WBS.01.01 | Mechanical | Area A | 2025-01-14 | 2025-06-09 | 2025-01-14 |  | 146 | 1511.8 | 0.96 | Complete | 2025-09-30
A0003 | Piping work package 003 | WBS.01.01 | Piping | Area A | 2025-07-10 | 2025-07-10 | 2025-07-10 |  | 64 | 1132.4 | 0.96 | In Progress | 2025-09-30
A0004 | Electrical work package 004 | WBS.01.01 | Unassigned | Area A | 2025-04-01 | 2025-07-01 | 2025-04-01 |  | 91 | 1099 | 0.96 | In Progress | 2025-09-30
A0006 | Civil work package 006 | WBS.01.01 | Civil | Area B | 2025-08-29 | 2025-10-20 | 2025-08-29 |  | 52 | 1747.7 | 0.6068 | In Progress | 2025-09-30
A0007 | Mechanical work package 007 | WBS.01.01 | Mechanical | Area B | 2025-06-22 | 2025-08-23 | 2025-06-22 |  | 62 | 1505.4 | 0.96 | In Progress | 2025-09-30
A0008 | Piping work package 008 | WBS.01.01 | Piping | Area B | 2025-02-07 | 2025-07-05 | 2025-02-07 |  | 148 | 1408.3 | 0.96 | In Progress | 2025-09-30
A0009 | Electrical work package 009 | WBS.01.01 | Electrical | Area B | 2026-01-12 | 2026-04-26 |  |  | 104 | 649.1 | 0 | Not Started | 2025-09-30
A0010 | Instrumentation work package 010 | WBS.01.01 | Instrumentation | Area B | 2026-01-22 | 2026-04-18 |  |  | 86 | 285.7 | 0 | Not Started | 2025-09-30
A0011 | Civil work package 011 | WBS.01.02 | Civil | Area C | 2025-08-18 | 2025-11-07 | 2025-08-18 |  | 81 | 123.7 | 0.3988 | In Progress | 2025-09-30
A0012 | Mechanical work package 012 | WBS.01.02 | Mechanical | Area C | 2026-01-31 | 2026-03-31 |  |  | 59 | 785.9 | 0 | Not Started | 2025-09-30
A0013 | Piping work package 013 | WBS.01.02 | Piping | Area C | 2025-12-17 | 2026-02-07 |  |  | 52 | 1615.2 | 0 | Not Started | 2025-09-30
A0014 | Electrical work package 014 | WBS.01.02 | Electrical | Area C | 2025-12-23 | 2026-05-05 |  |  | 133 | 92 | 0 | Not Started | 2025-09-30
A0015 | Instrumentation work package 015 | WBS.01.02 | Instrumentation | Area C | 2026-02-15 | 2026-04-24 |  |  | 68 | 972.3 | 0 | Not Started | 2025-09-30
A0016 | Civil work package 016 | WBS.01.02 | Civil | Area A | 2025-05-08 | 2025-06-11 | 2025-05-08 |  | 34 | 1128.5 | 0.96 | In Progress | 2025-09-30
A0017 | Mechanical work package 017 | WBS.01.02 | Mechanical | Area A | 2026-03-05 | 2026-05-03 |  |  | 59 | 1236.1 | 0 | Not Started | 2025-09-30
A0018 | Piping work package 018 | WBS.01.02 | Piping | Area A | 2025-10-05 | 2026-01-07 |  |  | 94 | 235.3 | 0 | Not Started | 2025-09-30
A0019 | Electrical work package 019 | WBS.01.02 | Electrical | Area A | 2025-10-24 | 2025-11-24 |  |  | 31 | 960.8 | 0 | Not Started | 2025-09-30
A0020 | Instrumentation work package 020 | WBS.01.02 | Instrumentation | Area A | 2026-02-12 | 2026-03-30 |  |  | 46 | 666.6 | 0 | Not Started | 2025-09-30
A0021 | Civil work package 021 | WBS.01.03 | Civil | Area B | 2025-08-21 | 2025-10-19 | 2025-08-21 |  | 59 | 240.1 | 0.6628 | In Progress | 2025-09-30
A0022 | Mechanical work package 022 | WBS.01.03 | Mechanical | Area B | 2025-11-14 | 2026-03-31 |  |  | 137 | 1605.8 | 0 | Not Started | 2025-09-30
A0023 | Piping work package 023 | WBS.01.03 | Piping | Area B | 2025-01-08 | 2025-02-26 | 2025-01-08 | 2025-02-26 | 49 | 1023.8 | 0.9988 | Complete | 2025-09-30
A0024 | Electrical work package 024 | WBS.01.03 | Electrical | Area B | 2025-05-25 | 2025-09-21 | 2025-05-25 | 2025-09-21 | 119 | 1197.4 | 0.9965 | Complete | 2025-09-30
A0025 | Instrumentation work package 025 | WBS.01.03 | Instrumentation | Area B | 2025-04-30 | 2025-06-28 | 2025-04-30 |  | 59 | 1753.6 | 0.96 | In Progress | 2025-09-30
A0026 | Civil work package 026 | WBS.01.03 | Civil | Area C | 2025-09-11 | 2025-12-09 | 2025-09-11 |  | 89 | 415.8 | 0.2284 | In Progress | 2025-09-30
A0027 | Mechanical work package 027 | WBS.01.03 | Mechanical | Area C | 2025-01-12 | 2025-06-02 | 2025-01-12 | 2025-06-02 | 141 | 816.5 | 1 | Complete | 2025-09-30
A0028 | Piping work package 028 | WBS.01.03 | Piping | Area C | 2025-03-19 | 2025-06-23 | 2025-03-19 |  | 96 | 1690.2 | 0.96 | In Progress | 2025-09-30
A0029 | Electrical work package 029 | WBS.01.03 | Electrical | Area C | 2026-01-18 | 2026-05-16 |  |  | 118 | 1278.9 | 0 | Not Started | 2025-09-30
A0030 | Instrumentation work package 030 | WBS.01.03 | Instrumentation | Area C | 2026-01-13 | 2026-06-01 |  |  | 139 | 959.5 | 0 | Not Started | 2025-09-30
A0031 | Civil work package 031 | WBS.01.04 | Civil | Area A | 2026-01-23 | 2026-04-03 |  |  | 70 | 726 | 0 | Not Started | 2025-09-30
A0032 | Mechanical work package 032 | WBS.01.04 | Mechanical | Area A | 2025-05-09 | 2025-08-17 | 2025-05-09 |  | 100 | 132.5 | 0.96 | In Progress | 2025-09-30
A0033 | Piping work package 033 | WBS.01.04 | Piping | Area A | 2025-12-03 | 2026-01-27 |  |  | 55 | 1151.4 | 0 | Not Started | 2025-09-30
A0034 | Electrical work package 034 | WBS.01.04 | Electrical | Area A | 2025-11-14 | 2026-04-10 |  |  | 147 | 968 | 0 | Not Started | 2025-09-30
A0035 | Instrumentation work package 035 | WBS.01.04 | Instrumentation | Area A | 2025-01-16 | 2025-06-10 | 2025-01-16 |  | 145 | 1517.9 | 0.9637 | In Progress | 2025-09-30
A0036 | Civil work package 036 | WBS.01.04 | Civil | Area B | 2025-08-30 | 2025-12-23 | 2025-08-30 |  | 115 | 1215.5 | 0.2263 | In Progress | 2025-09-30
A0037 | Mechanical work package 037 | WBS.01.04 | Mechanical | Area B | 2025-06-08 | 2025-10-06 | 2025-06-08 |  | 120 | 104.8 | 0.8029 | In Progress | 2025-09-30
A0038 | Piping work package 038 | WBS.01.04 | Piping | Area B | 2025-08-05 | 2025-10-30 | 2025-08-05 |  | 86 | 377.9 | 0.6022 | In Progress | 2025-09-30
A0039 | Electrical work package 039 | WBS.01.04 | Electrical | Area B | 2025-06-16 | 2025-09-29 | 2025-06-16 | 2025-09-29 | 105 | 945.4 | 1 | Complete | 2025-09-30
A0040 | Instrumentation work package 040 | WBS.01.04 | Instrumentation | Area B | 2025-01-17 | 2025-04-27 | 2025-01-17 |  | 100 | 1697.2 | 0.96 | In Progress | 2025-09-30
A0041 | Civil work package 041 | WBS.01.05 | Civil | Area C | 2026-02-14 | 2026-05-01 |  |  | 76 | 1733.2 | 0 | Not Started | 2025-09-30
A0042 | Mechanical work package 042 | WBS.01.05 | Mechanical | Area C | 2026-01-04 | 2026-02-05 |  |  | 32 | 1480.9 | 0 | Not Started | 2025-09-30
A0043 | Piping work package 043 | WBS.01.05 | Piping | Area C | 2025-11-18 | 2026-03-24 |  |  | 126 | 565.1 | 0 | Not Started | 2025-09-30
A0044 | Electrical work package 044 | WBS.01.05 | Electrical | Area C | 2025-06-14 | 2025-10-15 | 2025-06-14 |  | 123 | 666.2 | 0.9283 | In Progress | 2025-09-30
A0045 | Instrumentation work package 045 | WBS.01.05 | Instrumentation | Area C | 2025-02-19 | 2025-07-07 | 2025-02-19 | 2025-07-07 | 138 | 949 | 1 | Complete | 2025-09-30
A0046 | Civil work package 046 | WBS.01.05 | Civil | Area A | 2026-02-18 | 2026-05-27 |  |  | 98 | 1166.8 | 0 | Not Started | 2025-09-30
A0047 | Mechanical work package 047 | WBS.01.05 | Mechanical | Area A | 2025-12-12 | 2026-04-15 |  |  | 124 | 236.9 | 0 | Not Started | 2025-09-30
A0048 | Piping work package 048 | WBS.01.05 | Piping | Area A | 2025-06-05 | 2025-07-19 | 2025-06-05 |  | 44 | 325.9 | 0.9825 | In Progress | 2025-09-30
A0049 | Electrical work package 049 | WBS.01.05 | Electrical | Area A | 2025-02-06 | 2025-06-14 | 2025-02-06 |  | 128 | 1294.7 | 0.96 | In Progress | 2025-09-30
A0050 | Instrumentation work package 050 | WBS.01.05 | Instrumentation | Area A | 2025-12-06 | 2026-03-13 |  |  | 97 | 809.7 | 0 | Not Started | 2025-09-30
A0051 | Civil work package 051 | WBS.02.01 | Civil | Area B | 2025-01-30 | 2025-03-15 | 2025-01-30 |  | 44 | 282.1 | 0.9794 | In Progress | 2025-09-30
A0052 | Mechanical work package 052 | WBS.02.01 | Mechanical | Area B | 2025-05-08 | 2025-09-19 | 2025-05-08 | 2025-09-19 | 134 | 464.6 | 1 | Complete | 2025-09-30
A0053 | Piping work package 053 | WBS.02.01 | Piping | Area B | 2026-02-26 | 2026-05-29 |  |  | 92 | 1162.6 | 0 | Not Started | 2025-09-30
A0054 | Electrical work package 054 | WBS.02.01 | Electrical | Area B | 2025-01-25 | 2025-03-29 | 2025-01-25 | 2025-03-29 | 63 | 1714.7 | 1 | Complete | 2025-09-30
A0055 | Instrumentation work package 055 | WBS.02.01 | Instrumentation | Area B | 2025-07-24 | 2025-10-04 | 2025-07-24 |  | 72 | 1083.9 | 0.7769 | In Progress | 2025-09-30
A0056 | Civil work package 056 | WBS.02.01 | Civil | Area C | 2025-10-27 | 2025-12-15 |  |  | 49 | 1646.8 | 0 | Not Started | 2025-09-30
A0057 | Mechanical work package 057 | WBS.02.01 | Mechanical | Area C | 2026-03-06 | 2026-04-23 |  |  | 48 | 1101.9 | 0 | Not Started | 2025-09-30
A0058 | Piping work package 058 | WBS.02.01 | Piping | Area C | 2025-01-30 | 2025-06-12 | 2025-01-30 | 2025-06-12 | 133 | 1478.2 | 1 | Complete | 2025-09-30
A0059 | Electrical work package 059 | WBS.02.01 | Electrical | Area C | 2025-07-18 | 2025-09-01 | 2025-07-18 |  | 45 | 1721 | 0.9914 | In Progress | 2025-09-30
A0060 | Instrumentation work package 060 | WBS.02.01 | Instrumentation | Area C | 2025-02-23 | 2025-06-13 | 2025-02-23 | 2025-06-13 | 110 | 974.9 | 1 | Complete | 2025-09-30
A0061 | Civil work package 061 | WBS.02.02 | Civil | Area A | 2026-01-17 | 2026-04-05 |  |  | 78 | 310.5 | 0 | Not Started | 2025-09-30
A0062 | Mechanical work package 062 | WBS.02.02 | Mechanical | Area A | 2025-03-05 | 2025-04-05 | 2025-03-05 |  | 31 | 683 | 0.9736 | In Progress | 2025-09-30
A0063 | Piping work package 063 | WBS.02.02 | Piping | Area A | 2025-08-15 | 2025-12-17 | 2025-08-15 |  | 124 | 762.1 | 0.3565 | In Progress | 2025-09-30
A0064 | Electrical work package 064 | WBS.02.02 | Electrical | Area A | 2025-08-05 | 2025-10-13 | 2025-08-05 |  | 69 | 1169.4 | 0.6839 | In Progress | 2025-09-30
A0065 | Instrumentation work package 065 | WBS.02.02 | Instrumentation | Area A | 2026-01-26 | 2026-04-22 |  |  | 86 | 1228.2 | 0 | Not Started | 2025-09-30
A0066 | Civil work package 066 | WBS.02.02 | Civil | Area B | 2025-04-04 | 2025-06-16 | 2025-04-04 |  | 73 | 945.9 | 0.9733 | In Progress | 2025-09-30
A0067 | Mechanical work package 067 | WBS.02.02 | Mechanical | Area B | 2025-12-18 | 2026-04-16 |  |  | 119 | 397.4 | 0 | Not Started | 2025-09-30
A0068 | Piping work package 068 | WBS.02.02 | Piping | Area B | 2025-07-23 | 2025-11-19 | 2025-07-23 |  | 119 | 143.1 | 0.5371 | In Progress | 2025-09-30
A0069 | Electrical work package 069 | WBS.02.02 | Electrical | Area B | 2025-02-21 | 2025-05-15 | 2025-02-21 |  | 83 | 996.1 | 0.96 | In Progress | 2025-09-30
A0070 | Instrumentation work package 070 | WBS.02.02 | Instrumentation | Area B | 2025-02-26 | 2025-07-12 | 2025-02-26 |  | 136 | 1101 | 0.96 | In Progress | 2025-09-30
A0071 | Civil work package 071 | WBS.02.03 | Civil | Area C | 2025-09-15 | 2026-01-12 | 2025-09-15 |  | 119 | 822.5 | 0.1548 | In Progress | 2025-09-30
A0072 | Mechanical work package 072 | WBS.02.03 | Mechanical | Area C | 2025-06-08 | 2025-11-03 | 2025-06-08 |  | 148 | 1121.9 | 0.652 | In Progress | 2025-09-30
A0073 | Piping work package 073 | WBS.02.03 | Piping | Area C | 2025-03-21 | 2025-08-05 | 2025-03-21 |  | 137 | 218 | 0.96 | In Progress | 2025-09-30
A0074 | Electrical work package 074 | WBS.02.03 | Electrical | Area C | 2026-02-26 | 2026-06-30 |  |  | 133 | 1485.4 | 0 | Not Started | 2025-09-30
A0075 | Instrumentation work package 075 | WBS.02.03 | Instrumentation | Area C | 2025-09-08 | 2025-11-10 | 2025-09-08 |  | 63 | 1403.5 | 0.3026 | In Progress | 2025-09-30
A0076 | Civil work package 076 | WBS.02.03 | Civil | Area A | 2025-02-24 | 2025-06-07 | 2025-02-24 |  | 103 | 576.4 | 0.96 | In Progress | 2025-09-30
A0077 | Mechanical work package 077 | WBS.02.03 | Mechanical | Area A | 2025-05-30 | 2025-07-15 | 2025-05-30 | 2025-07-15 | 46 | 189 | 1 | Complete | 2025-09-30
A0078 | Piping work package 078 | WBS.02.03 | Piping | Area A | 2025-11-28 | 2026-03-09 |  |  | 101 | 891.1 | 0 | Not Started | 2025-09-30
A0079 | Electrical work package 079 | WBS.02.03 | Electrical | Area A | 2026-02-13 | 2026-04-05 |  |  | 51 | 194.4 | 0 | Not Started | 2025-09-30
A0080 | Instrumentation work package 080 | WBS.02.03 | Instrumentation | Area A | 2025-04-02 | 2025-05-21 | 2025-04-02 | 2025-05-21 | 49 | 362.5 | 0.9992 | Complete | 2025-09-30
A0081 | Civil work package 081 | WBS.02.04 | Civil | Area B | 2025-06-23 | 2025-10-28 | 2025-06-23 |  | 127 | 835.3 | 0.7487 | In Progress | 2025-09-30
A0082 | Mechanical work package 082 | WBS.02.04 | Mechanical | Area B | 2025-04-15 | 2025-08-30 | 2025-04-15 |  | 137 | 740.3 | 0.9736 | In Progress | 2025-09-30
A0083 | Piping work package 083 | WBS.02.04 | Piping | Area B | 2025-03-06 | 2025-07-09 | 2025-03-06 |  | 125 | 1146.5 | 0.96 | In Progress | 2025-09-30
A0084 | Electrical work package 084 | WBS.02.04 | Electrical | Area B | 2025-04-22 | 2025-08-19 | 2025-04-22 |  | 119 | 137.7 | 0.96 | In Progress | 2025-09-30
A0085 | Instrumentation work package 085 | WBS.02.04 | Instrumentation | Area B | 2025-02-22 | 2025-07-03 | 2025-02-22 |  | 131 | 299.3 | 0.96 | In Progress | 2025-09-30
A0086 | Civil work package 086 | WBS.02.04 | Civil | Area C | 2025-11-11 | 2026-02-25 |  |  | 106 | 1273.6 | 0 | Not Started | 2025-09-30
A0087 | Mechanical work package 087 | WBS.02.04 | Mechanical | Area C | 2025-07-23 | 2025-12-13 | 2025-07-23 |  | 143 | 343.8 | 0.4789 | In Progress | 2025-09-30
A0088 | Piping work package 088 | WBS.02.04 | Piping | Area C | 2025-11-01 | 2026-03-21 |  |  | 140 | 1296.5 | 0 | Not Started | 2025-09-30
A0089 | Electrical work package 089 | WBS.02.04 | Electrical | Area C | 2026-02-11 | 2026-06-30 |  |  | 141 | 855.4 | 0 | Not Started | 2025-09-30
A0090 | Instrumentation work package 090 | WBS.02.04 | Instrumentation | Area C | 2025-01-29 | 2025-04-09 | 2025-01-29 |  | 70 | 1460.9 | 0.96 | In Progress | 2025-09-30
A0091 | Civil work package 091 | WBS.02.05 | Civil | Area A | 2025-06-03 | 2025-08-13 | 2025-06-03 |  | 71 | 1348.5 | 0.96 | In Progress | 2025-09-30
A0092 | Mechanical work package 092 | WBS.02.05 | Mechanical | Area A | 2025-08-08 | 2025-10-27 | 2025-08-08 |  | 80 | 1653.5 | 0.5708 | In Progress | 2025-09-30
A0093 | Piping work package 093 | WBS.02.05 | Piping | Area A | 2025-02-11 | 2025-07-10 | 2025-02-11 |  | 149 | 943.8 | 0.96 | In Progress | 2025-09-30
A0094 | Electrical work package 094 | WBS.02.05 | Electrical | Area A | 2025-04-04 | 2025-05-26 | 2025-04-04 |  | 52 | 142.9 | 0.9662 | In Progress | 2025-09-30
A0095 | Instrumentation work package 095 | WBS.02.05 | Instrumentation | Area A | 2025-08-19 | 2025-11-09 | 2025-08-19 |  | 82 | 769.3 | 0.4665 | In Progress | 2025-09-30
A0096 | Civil work package 096 | WBS.02.05 | Civil | Area B | 2025-10-09 | 2025-12-27 |  |  | 79 | 123.7 | 0 | Not Started | 2025-09-30
A0097 | Mechanical work package 097 | WBS.02.05 | Mechanical | Area B | 2025-01-14 | 2025-02-25 | 2025-01-14 |  | 42 | 1455.9 | 0.96 | In Progress | 2025-09-30
A0098 | Piping work package 098 | WBS.02.05 | Piping | Area B | 2025-11-12 | 2026-03-24 |  |  | 132 | 1508 | 0 | Not Started | 2025-09-30
A0099 | Electrical work package 099 | WBS.02.05 | Electrical | Area B | 2025-01-11 | 2025-02-20 | 2025-01-11 |  | 40 | 437.6 | 0.96 | In Progress | 2025-09-30
A0100 | Instrumentation work package 100 | WBS.02.05 | Instrumentation | Area B | 2025-12-23 | 2026-03-04 |  |  | 71 | 526.2 | 0 | Not Started | 2025-09-30
A0101 | Civil work package 101 | WBS.03.01 | Civil | Area C | 2025-08-31 | 2025-11-21 | 2025-08-31 |  | 82 | 586.5 | 0.4074 | In Progress | 2025-09-30
A0102 | Mechanical work package 102 | WBS.03.01 | Mechanical | Area C | 2026-01-25 | 2026-05-30 |  |  | 125 | 811.4 | 0 | Not Started | 2025-09-30
A0103 | Piping work package 103 | WBS.03.01 | Piping | Area C | 2025-03-06 | 2025-07-14 | 2025-03-06 |  | 130 | 1773.2 | 0.96 | In Progress | 2025-09-30
A0104 | Electrical work package 104 | WBS.03.01 | Electrical | Area C | 2025-05-03 | 2025-08-07 | 2025-05-03 | 2025-08-07 | 96 | 1200.4 | 1 | Complete | 2025-09-30
A0105 | Instrumentation work package 105 | WBS.03.01 | Instrumentation | Area C | 2025-03-22 | 2025-08-08 | 2025-03-22 |  | 139 | 800.3 | 0.96 | In Progress | 2025-09-30
A0106 | Civil work package 106 | WBS.03.01 | Civil | Area A | 2025-02-10 | 2025-05-23 | 2025-02-10 |  | 102 | 502 | 0.96 | In Progress | 2025-09-30
A0107 | Mechanical work package 107 | WBS.03.01 | Mechanical | Area A | 2025-09-06 | 2025-12-02 | 2025-09-06 |  | 87 | 1221.5 | 0.2887 | In Progress | 2025-09-30
A0108 | Piping work package 108 | WBS.03.01 | Piping | Area A | 2025-08-07 | 2025-11-16 | 2025-08-07 |  | 101 | 654.9 | 0.5785 | In Progress | 2025-09-30
A0109 | Electrical work package 109 | WBS.03.01 | Electrical | Area A | 2025-04-21 | 2025-08-27 | 2025-04-21 |  | 128 | 1455 | 0.9736 | In Progress | 2025-09-30
A0110 | Instrumentation work package 110 | WBS.03.01 | Instrumentation | Area A | 2026-02-04 | 2026-03-22 |  |  | 46 | 1714.4 | 0 | Not Started | 2025-09-30
A0111 | Civil work package 111 | WBS.03.02 | Civil | Area B | 2025-12-18 | 2026-04-06 |  |  | 109 | 1270.7 | 0 | Not Started | 2025-09-30
A0112 | Mechanical work package 112 | WBS.03.02 | Mechanical | Area B | 2025-03-24 | 2025-06-30 | 2025-03-24 |  | 98 | 1654.6 | 0.96 | In Progress | 2025-09-30
A0113 | Piping work package 113 | WBS.03.02 | Piping | Area B | 2026-01-11 | 2026-05-22 |  |  | 131 | 628.9 | 0 | Not Started | 2025-09-30
A0114 | Electrical work package 114 | WBS.03.02 | Electrical | Area B | 2025-02-08 | 2025-06-01 | 2025-02-08 |  | 113 | 664.6 | 0.9916 | In Progress | 2025-09-30
A0115 | Instrumentation work package 115 | WBS.03.02 | Instrumentation | Area B | 2025-05-23 | 2025-09-05 | 2025-05-23 | 2025-09-05 | 105 | 1603.9 | 0.9969 | Complete | 2025-09-30
A0116 | Civil work package 116 | WBS.03.02 | Civil | Area C | 2025-07-31 | 2025-11-13 | 2025-07-31 |  | 105 | 1582.7 | 0.5948 | In Progress | 2025-09-30
A0117 | Mechanical work package 117 | WBS.03.02 | Mechanical | Area C | 2025-04-18 | 2025-05-31 | 2025-04-18 |  | 43 | 690 | 0.96 | In Progress | 2025-09-30
A0118 | Piping work package 118 | WBS.03.02 | Piping | Area C | 2025-06-20 | 2025-10-09 | 2025-06-20 |  | 111 | 455.4 | 0.9712 | In Progress | 2025-09-30
A0119 | Electrical work package 119 | WBS.03.02 | Electrical | Area C | 2025-09-26 | 2025-11-15 | 2025-09-26 |  | 50 | 1784.8 | 0.1312 | In Progress | 2025-09-30
A0120 | Instrumentation work package 120 | WBS.03.02 | Instrumentation | Area C | 2025-04-15 | 2025-06-05 | 2025-04-15 |  | 51 | 459.2 | 0.96 | In Progress | 2025-09-30
A0121 | Civil work package 121 | WBS.03.03 | Civil | Area A | 2025-11-01 | 2025-12-19 |  |  | 48 | 1483.2 | 0 | Not Started | 2025-09-30
A0122 | Mechanical work package 122 | WBS.03.03 | Mechanical | Area A | 2025-02-14 | 2025-06-29 | 2025-02-14 |  | 135 | 536.8 | 0.96 | In Progress | 2025-09-30
A0123 | Piping work package 123 | WBS.03.03 | Piping | Area A | 2025-02-12 | 2025-05-02 | 2025-02-12 |  | 79 | 721 | 0.96 | In Progress | 2025-09-30
A0124 | Electrical work package 124 | WBS.03.03 | Electrical | Area A | 2026-01-07 | 2026-04-06 |  |  | 89 | 906.6 | 0 | Not Started | 2025-09-30
A0125 | Instrumentation work package 125 | WBS.03.03 | Instrumentation | Area A | 2025-04-30 | 2025-09-12 | 2025-04-30 | 2025-09-12 | 135 | 1451.6 | 1 | Complete | 2025-09-30
A0126 | Civil work package 126 | WBS.03.03 | Civil | Area B | 2025-09-29 | 2026-01-27 |  |  | 120 | 352.8 | 0 | Not Started | 2025-09-30
A0127 | Mechanical work package 127 | WBS.03.03 | Mechanical | Area B | 2025-03-16 | 2025-07-22 | 2025-03-16 |  | 128 | 1511.3 | 0.96 | In Progress | 2025-09-30
A0128 | Piping work package 128 | WBS.03.03 | Piping | Area B | 2025-10-05 | 2026-01-07 |  |  | 94 | 1421.3 | 0 | Not Started | 2025-09-30
A0129 | Electrical work package 129 | WBS.03.03 | Electrical | Area B | 2025-10-05 | 2026-02-23 |  |  | 141 | 256.3 | 0 | Not Started | 2025-09-30
A0130 | Instrumentation work package 130 | WBS.03.03 | Instrumentation | Area B | 2025-02-03 | 2025-05-13 | 2025-02-03 |  | 99 | 674.9 | 0.9612 | In Progress | 2025-09-30
A0131 | Civil work package 131 | WBS.03.04 | Civil | Area C | 2025-10-26 | 2026-01-17 |  |  | 83 | 550.6 | 0 | Not Started | 2025-09-30
A0132 | Mechanical work package 132 | WBS.03.04 | Mechanical | Area C | 2025-10-31 | 2025-12-26 |  |  | 56 | 221.7 | 0 | Not Started | 2025-09-30
A0133 | Piping work package 133 | WBS.03.04 | Piping | Area C | 2025-07-05 | 2025-10-19 | 2025-07-05 |  | 106 | 763.9 | 0.7336 | In Progress | 2025-09-30
A0134 | Electrical work package 134 | WBS.03.04 | Electrical | Area C | 2025-04-07 | 2025-05-10 | 2025-04-07 |  | 33 | 1200.9 | 0.96 | In Progress | 2025-09-30
A0135 | Instrumentation work package 135 | WBS.03.04 | Instrumentation | Area C | 2025-12-03 | 2026-04-13 |  |  | 131 | 1389 | 0 | Not Started | 2025-09-30
A0136 | Civil work package 136 | WBS.03.04 | Civil | Area A | 2025-02-25 | 2025-04-11 | 2025-02-25 |  | 45 | 1259.2 | 0.96 | In Progress | 2025-09-30
A0137 | Mechanical work package 137 | WBS.03.04 | Mechanical | Area A | 2025-05-01 | 2025-09-03 | 2025-05-01 |  | 125 | 613.8 | 0.96 | In Progress | 2025-09-30
A0138 | Piping work package 138 | WBS.03.04 | Piping | Area A | 2025-10-31 | 2026-03-13 |  |  | 133 | 1421.3 | 0 | Not Started | 2025-09-30
A0139 | Electrical work package 139 | WBS.03.04 | Electrical | Area A | 2025-09-28 | 2026-01-20 |  |  | 114 | 1042.6 | 0 | Not Started | 2025-09-30
A0140 | Instrumentation work package 140 | WBS.03.04 | Instrumentation | Area A | 2025-01-20 | 2025-02-28 | 2025-01-20 |  | 39 | 762.7 | 0.96 | In Progress | 2025-09-30
A0141 | Civil work package 141 | WBS.03.05 | Civil | Area B | 2025-03-19 | 2025-04-30 | 2025-03-19 |  | 42 | 1174.7 | 0.9923 | In Progress | 2025-09-30
A0142 | Mechanical work package 142 | WBS.03.05 | Mechanical | Area B | 2025-11-09 | 2026-03-15 |  |  | 126 | 663.9 | 0 | Not Started | 2025-09-30
A0143 | Piping work package 143 | WBS.03.05 | Piping | Area B | 2025-08-20 | 2025-12-15 | 2025-08-20 |  | 117 | 220.4 | 0.3028 | In Progress | 2025-09-30
A0144 | Electrical work package 144 | WBS.03.05 | Electrical | Area B | 2026-03-01 | 2026-05-10 |  |  | 70 | 393.2 | 0 | Not Started | 2025-09-30
A0145 | Instrumentation work package 145 | WBS.03.05 | Instrumentation | Area B | 2025-04-14 | 2025-09-10 | 2025-04-14 |  | 149 | 1756.6 | 0.96 | In Progress | 2025-09-30
A0146 | Civil work package 146 | WBS.03.05 | Civil | Area C | 2026-01-14 | 2026-05-11 |  |  | 117 | 1357.5 | 0 | Not Started | 2025-09-30
A0147 | Mechanical work package 147 | WBS.03.05 | Mechanical | Area C | 2025-07-13 | 2025-11-07 | 2025-07-13 |  | 117 | 917.1 | 0.6499 | In Progress | 2025-09-30
A0148 | Piping work package 148 | WBS.03.05 | Piping | Area C | 2026-02-02 | 2026-03-29 |  |  | 55 | 1151.5 | 0 | Not Started | 2025-09-30
A0149 | Electrical work package 149 | WBS.03.05 | Electrical | Area C | 2025-03-24 | 2025-05-21 | 2025-03-24 |  | 58 | 1750.8 | 0.96 | In Progress | 2025-09-30
A0150 | Instrumentation work package 150 | WBS.03.05 | Instrumentation | Area C | 2025-07-16 | 2025-10-15 | 2025-07-16 |  | 91 | 697.9 | 0.8278 | In Progress | 2025-09-30
A0151 | Civil work package 151 | WBS.04.01 | Civil | Area A | 2025-12-04 | 2026-01-18 |  |  | 45 | 1748.1 | 0 | Not Started | 2025-09-30
A0152 | Mechanical work package 152 | WBS.04.01 | Mechanical | Area A | 2025-07-10 | 2025-09-07 | 2025-07-10 | 2025-09-07 | 59 | 1141.5 | 1 | Complete | 2025-09-30
A0153 | Piping work package 153 | WBS.04.01 | Piping | Area A | 2026-01-03 | 2026-05-09 |  |  | 126 | 1086.8 | 0 | Not Started | 2025-09-30
A0154 | Electrical work package 154 | WBS.04.01 | Electrical | Area A | 2025-08-22 | 2026-01-11 | 2025-08-22 |  | 142 | 147.7 | 0.183 | In Progress | 2025-09-30
A0155 | Instrumentation work package 155 | WBS.04.01 | Instrumentation | Area A | 2025-01-23 | 2025-03-11 | 2025-01-23 |  | 47 | 1777 | 0.9696 | In Progress | 2025-09-30
A0156 | Civil work package 156 | WBS.04.01 | Civil | Area B | 2025-08-04 | 2025-11-22 | 2025-08-04 |  | 110 | 320.2 | 0.4021 | In Progress | 2025-09-30
A0157 | Mechanical work package 157 | WBS.04.01 | Mechanical | Area B | 2026-02-27 | 2026-04-09 |  |  | 41 | 1236.9 | 0 | Not Started | 2025-09-30
A0158 | Piping work package 158 | WBS.04.01 | Piping | Area B | 2026-02-16 | 2026-06-07 |  |  | 111 | 935.1 | 0 | Not Started | 2025-09-30
A0159 | Electrical work package 159 | WBS.04.01 | Electrical | Area B | 2025-04-08 | 2025-07-26 | 2025-04-08 |  | 109 | 757.4 | 0.978 | In Progress | 2025-09-30
A0160 | Instrumentation work package 160 | WBS.04.01 | Instrumentation | Area B | 2026-01-15 | 2026-05-18 |  |  | 123 | 1055.3 | 0 | Not Started | 2025-09-30
A0161 | Civil work package 161 | WBS.04.02 | Civil | Area C | 2025-12-19 | 2026-04-19 |  |  | 121 | 1452.2 | 0 | Not Started | 2025-09-30
A0162 | Mechanical work package 162 | WBS.04.02 | Mechanical | Area C | 2025-05-25 | 2025-08-06 | 2025-05-25 |  | 73 | 761.4 | 0.96 | In Progress | 2025-09-30
A0163 | Piping work package 163 | WBS.04.02 | Piping | Area C | 2025-04-13 | 2025-05-21 | 2025-04-13 |  | 38 | 1117.9 | 0.9656 | In Progress | 2025-09-30
A0164 | Electrical work package 164 | WBS.04.02 | Electrical | Area C | 2025-08-17 | 2025-11-12 | 2025-08-17 |  | 87 | 124.1 | 0.5154 | In Progress | 2025-09-30
A0165 | Instrumentation work package 165 | WBS.04.02 | Instrumentation | Area C | 2025-09-24 | 2026-01-23 | 2025-09-24 |  | 121 | 1478.3 | 0.0473 | In Progress | 2025-09-30
A0166 | Civil work package 166 | WBS.04.02 | Civil | Area A | 2025-01-31 | 2025-06-22 | 2025-01-31 |  | 142 | 684.8 | 0.96 | In Progress | 2025-09-30
A0167 | Mechanical work package 167 | WBS.04.02 | Mechanical | Area A | 2025-12-17 | 2026-03-21 |  |  | 94 | 615.4 | 0 | Not Started | 2025-09-30
A0168 | Piping work package 168 | WBS.04.02 | Piping | Area A | 2025-03-24 | 2025-07-13 | 2025-03-24 |  | 111 | 392.1 | 0.96 | In Progress | 2025-09-30
A0169 | Electrical work package 169 | WBS.04.02 | Electrical | Area A | 2026-02-24 | 2026-05-23 |  |  | 88 | 1466.3 | 0 | Not Started | 2025-09-30
A0170 | Instrumentation work package 170 | WBS.04.02 | Instrumentation | Area A | 2025-12-24 | 2026-05-09 |  |  | 136 | 472.3 | 0 | Not Started | 2025-09-30
A0171 | Civil work package 171 | WBS.04.03 | Civil | Area B | 2025-12-07 | 2026-02-07 |  |  | 62 | 1494.9 | 0 | Not Started | 2025-09-30
A0172 | Mechanical work package 172 | WBS.04.03 | Mechanical | Area B | 2025-09-15 | 2025-11-04 | 2025-09-15 |  | 50 | 1347.4 | 0.3019 | In Progress | 2025-09-30
A0173 | Piping work package 173 | WBS.04.03 | Piping | Area B | 2025-09-24 | 2025-12-28 | 2025-09-24 |  | 95 | 478.9 | 0.0984 | In Progress | 2025-09-30
A0174 | Electrical work package 174 | WBS.04.03 | Electrical | Area B | 2025-07-09 | 2025-11-02 | 2025-07-09 |  | 116 | 1271 | 0.7448 | In Progress | 2025-09-30
A0175 | Instrumentation work package 175 | WBS.04.03 | Instrumentation | Area B | 2025-02-11 | 2025-06-28 | 2025-02-11 |  | 137 | 410 | 0.96 | In Progress | 2025-09-30
A0176 | Civil work package 176 | WBS.04.03 | Civil | Area C | 2025-02-04 | 2025-06-10 | 2025-02-04 |  | 126 | 482 | 0.96 | In Progress | 2025-09-30
A0177 | Mechanical work package 177 | WBS.04.03 | Mechanical | Area C | 2025-05-29 | 2025-09-16 | 2025-05-29 |  | 110 | 1789.9 | 0.9708 | In Progress | 2025-09-30
A0178 | Piping work package 178 | WBS.04.03 | Piping | Area C | 2025-09-04 | 2026-01-26 | 2025-09-04 |  | 144 | 381.5 | 0.1541 | In Progress | 2025-09-30
A0179 | Electrical work package 179 | WBS.04.03 | Electrical | Area C | 2025-11-27 | 2026-02-06 |  |  | 71 | 1223.6 | 0 | Not Started | 2025-09-30
A0180 | Instrumentation work package 180 | WBS.04.03 | Instrumentation | Area C | 2025-08-18 | 2025-11-30 | 2025-08-18 |  | 104 | 233.3 | 0.4348 | In Progress | 2025-09-30
A0181 | Civil work package 181 | WBS.04.04 | Civil | Area A | 2025-01-21 | 2025-03-28 | 2025-01-21 |  | 66 | 532.6 | 0.96 | In Progress | 2025-09-30
A0182 | Mechanical work package 182 | WBS.04.04 | Mechanical | Area A | 2025-09-21 | 2025-12-21 | 2025-09-21 |  | 91 | 1661.4 | 0.0851 | In Progress | 2025-09-30
A0183 | Piping work package 183 | WBS.04.04 | Piping | Area A | 2026-01-14 | 2026-05-20 |  |  | 126 | 1438.9 | 0 | Not Started | 2025-09-30
A0184 | Electrical work package 184 | WBS.04.04 | Electrical | Area A | 2025-06-03 | 2025-10-28 | 2025-06-03 |  | 147 | 1182.5 | 0.8309 | In Progress | 2025-09-30
A0185 | Instrumentation work package 185 | WBS.04.04 | Instrumentation | Area A | 2025-03-22 | 2025-06-20 | 2025-03-22 |  | 90 | 765.7 | 0.96 | In Progress | 2025-09-30
A0186 | Civil work package 186 | WBS.04.04 | Civil | Area B | 2026-02-25 | 2026-05-17 |  |  | 81 | 616.3 | 0 | Not Started | 2025-09-30
A0187 | Mechanical work package 187 | WBS.04.04 | Mechanical | Area B | 2025-09-29 | 2026-01-15 |  |  | 108 | 341.5 | 0 | Not Started | 2025-09-30
A0188 | Piping work package 188 | WBS.04.04 | Piping | Area B | 2026-03-04 | 2026-05-01 |  |  | 58 | 324.7 | 0 | Not Started | 2025-09-30
A0189 | Electrical work package 189 | WBS.04.04 | Electrical | Area B | 2025-08-13 | 2026-01-09 | 2025-08-13 |  | 149 | 1480 | 0.3331 | In Progress | 2025-09-30
A0190 | Instrumentation work package 190 | WBS.04.04 | Instrumentation | Area B | 2025-03-03 | 2025-07-17 | 2025-03-03 |  | 136 | 853.6 | 0.96 | In Progress | 2025-09-30
A0191 | Civil work package 191 | WBS.04.05 | Civil | Area C | 2025-12-02 | 2026-01-02 |  |  | 31 | 795.8 | 0 | Not Started | 2025-09-30
A0192 | Mechanical work package 192 | WBS.04.05 | Mechanical | Area C | 2025-01-11 | 2025-03-10 | 2025-01-11 |  | 58 | 1758.5 | 0.98 | In Progress | 2025-09-30
A0193 | Piping work package 193 | WBS.04.05 | Piping | Area C | 2025-07-20 | 2025-11-28 | 2025-07-20 |  | 131 | 248.7 | 0.5552 | In Progress | 2025-09-30
A0194 | Electrical work package 194 | WBS.04.05 | Electrical | Area C | 2025-06-16 | 2025-09-01 | 2025-06-16 | 2025-09-01 | 77 | 870.2 | 1 | Complete | 2025-09-30
A0195 | Instrumentation work package 195 | WBS.04.05 | Instrumentation | Area C | 2025-04-25 | 2025-09-02 | 2025-04-25 | 2025-09-02 | 130 | 146.1 | 1 | Complete | 2025-09-30
A0196 | Civil work package 196 | WBS.04.05 | Civil | Area A | 2025-10-06 | 2026-01-17 |  |  | 103 | 194.6 | 0 | Not Started | 2025-09-30
A0197 | Mechanical work package 197 | WBS.04.05 | Mechanical | Area A | 2025-01-23 | 2025-03-04 | 2025-01-23 |  | 40 | 1312.1 | 0.96 | In Progress | 2025-09-30
A0198 | Piping work package 198 | WBS.04.05 | Piping | Area A | 2025-10-17 | 2025-12-08 |  |  | 52 | 379.5 | 0 | Not Started | 2025-09-30
A0199 | Electrical work package 199 | WBS.04.05 | Electrical | Area A | 2025-10-01 | 2025-12-15 |  |  | 75 | 433.8 | 0 | Not Started | 2025-09-30
A0200 | Instrumentation work package 200 | WBS.04.05 | Instrumentation | Area A | 2025-01-24 | 2025-06-19 | 2025-01-24 |  | 146 | 1453.8 | 0.96 | In Progress | 2025-09-30
A0201 | Civil work package 201 | WBS.05.01 | Civil | Area B | 2025-12-21 | 2026-04-08 |  |  | 108 | 300.3 | 0 | Not Started | 2025-09-30
A0202 | Mechanical work package 202 | WBS.05.01 | Mechanical | Area B | 2026-02-15 | 2026-04-14 |  |  | 58 | 289 | 0 | Not Started | 2025-09-30
A0203 | Piping work package 203 | WBS.05.01 | Piping | Area B | 2026-01-11 | 2026-05-22 |  |  | 131 | 1660.6 | 0 | Not Started | 2025-09-30
A0204 | Electrical work package 204 | WBS.05.01 | Electrical | Area B | 2025-12-05 | 2026-03-23 |  |  | 108 | 385.2 | 0 | Not Started | 2025-09-30
A0205 | Instrumentation work package 205 | WBS.05.01 | Instrumentation | Area B | 2025-08-11 | 2025-12-19 | 2025-08-11 |  | 130 | 1340.4 | 0.3193 | In Progress | 2025-09-30
A0206 | Civil work package 206 | WBS.05.01 | Civil | Area C | 2025-10-29 | 2026-03-12 |  |  | 134 | 1174.4 | 0 | Not Started | 2025-09-30
A0207 | Mechanical work package 207 | WBS.05.01 | Mechanical | Area C | 2025-12-16 | 2026-02-08 |  |  | 54 | 1034.7 | 0 | Not Started | 2025-09-30
A0208 | Piping work package 208 | WBS.05.01 | Piping | Area C | 2025-09-01 | 2025-10-01 | 2025-09-01 |  | 30 | 1388.9 | 0.811 | In Progress | 2025-09-30
A0209 | Electrical work package 209 | WBS.05.01 | Electrical | Area C | 2025-05-26 | 2025-07-12 | 2025-05-26 | 2025-07-12 | 47 | 605.6 | 1 | Complete | 2025-09-30
A0210 | Instrumentation work package 210 | WBS.05.01 | Instrumentation | Area C | 2025-06-23 | 2025-09-10 | 2025-06-23 |  | 79 | 1276.5 | 0.96 | In Progress | 2025-09-30
A0211 | Civil work package 211 | WBS.05.02 | Civil | Area A | 2025-10-09 | 2025-11-15 |  |  | 37 | 1077.6 | 0 | Not Started | 2025-09-30
A0212 | Mechanical work package 212 | WBS.05.02 | Mechanical | Area A | 2025-05-02 | 2025-09-08 | 2025-05-02 |  | 129 | 937 | 0.96 | In Progress | 2025-09-30
A0213 | Piping work package 213 | WBS.05.02 | Piping | Area A | 2025-12-11 | 2026-03-13 |  |  | 92 | 837.1 | 0 | Not Started | 2025-09-30
A0214 | Electrical work package 214 | WBS.05.02 | Electrical | Area A | 2025-09-20 | 2026-01-16 | 2025-09-20 |  | 118 | 1797.2 | 0.1022 | In Progress | 2025-09-30
A0215 | Instrumentation work package 215 | WBS.05.02 | Instrumentation | Area A | 2025-02-25 | 2025-05-15 | 2025-02-25 |  | 79 | 1524.5 | 0.96 | In Progress | 2025-09-30
A0216 | Civil work package 216 | WBS.05.02 | Civil | Area B | 2025-05-29 | 2025-07-01 | 2025-05-29 | 2025-07-01 | 33 | 121.6 | 1 | Complete | 2025-09-30
A0217 | Mechanical work package 217 | WBS.05.02 | Mechanical | Area B | 2025-04-27 | 2025-07-17 | 2025-04-27 |  | 81 | 1581.1 | 0.96 | In Progress | 2025-09-30
A0218 | Piping work package 218 | WBS.05.02 | Piping | Area B | 2025-03-04 | 2025-04-12 | 2025-03-04 |  | 39 | 1332.1 | 0.96 | In Progress | 2025-09-30
A0219 | Electrical work package 219 | WBS.05.02 | Electrical | Area B | 2025-09-25 | 2025-11-10 | 2025-09-25 |  | 46 | 1372.4 | 0.0849 | In Progress | 2025-09-30
A0220 | Instrumentation work package 220 | WBS.05.02 | Instrumentation | Area B | 2026-01-30 | 2026-03-30 |  |  | 59 | 547.8 | 0 | Not Started | 2025-09-30
A0221 | Civil work package 221 | WBS.05.03 | Civil | Area C | 2025-01-20 | 2025-02-26 | 2025-01-20 |  | 37 | 1639.1 | 0.96 | In Progress | 2025-09-30
A0222 | Mechanical work package 222 | WBS.05.03 | Mechanical | Area C | 2025-01-15 | 2025-05-04 | 2025-01-15 |  | 109 | 1737 | 0.96 | In Progress | 2025-09-30
A0223 | Piping work package 223 | WBS.05.03 | Piping | Area C | 2025-04-01 | 2025-07-07 | 2025-04-01 | 2025-07-07 | 97 | 878 | 1 | Complete | 2025-09-30
A0224 | Electrical work package 224 | WBS.05.03 | Electrical | Area C | 2026-01-06 | 2026-04-13 |  |  | 97 | 980.2 | 0 | Not Started | 2025-09-30
A0225 | Instrumentation work package 225 | WBS.05.03 | Instrumentation | Area C | 2025-08-27 | 2025-10-05 | 2025-08-27 |  | 39 | 868.3 | 0.7868 | In Progress | 2025-09-30
A0226 | Civil work package 226 | WBS.05.03 | Civil | Area A | 2025-10-12 | 2026-01-15 |  |  | 95 | 187.1 | 0 | Not Started | 2025-09-30
A0227 | Mechanical work package 227 | WBS.05.03 | Mechanical | Area A | 2025-03-17 | 2025-05-25 | 2025-03-17 |  | 69 | 1381.6 | 0.96 | In Progress | 2025-09-30
A0228 | Piping work package 228 | WBS.05.03 | Piping | Area A | 2026-03-05 | 2026-06-30 |  |  | 122 | 126.7 | 0 | Not Started | 2025-09-30
A0229 | Electrical work package 229 | WBS.05.03 | Electrical | Area A | 2025-02-20 | 2025-06-08 | 2025-02-20 |  | 108 | 1494 | 0.96 | In Progress | 2025-09-30
A0230 | Instrumentation work package 230 | WBS.05.03 | Instrumentation | Area A | 2025-09-11 | 2025-12-26 | 2025-09-11 |  | 106 | 1452.4 | 0.1421 | In Progress | 2025-09-30
A0231 | Civil work package 231 | WBS.05.04 | Civil | Area B | 2025-12-13 | 2026-02-19 |  |  | 68 | 1554.3 | 0 | Not Started | 2025-09-30
A0232 | Mechanical work package 232 | WBS.05.04 | Mechanical | Area B | 2025-07-14 | 2025-10-25 | 2025-07-14 |  | 103 | 223.6 | 0.786 | In Progress | 2025-09-30
A0233 | Piping work package 233 | WBS.05.04 | Piping | Area B | 2026-03-05 | 2026-06-23 |  |  | 110 | 1171.6 | 0 | Not Started | 2025-09-30
A0234 | Electrical work package 234 | WBS.05.04 | Electrical | Area B | 2025-11-11 | 2026-03-27 |  |  | 136 | 216.6 | 0 | Not Started | 2025-09-30
A0235 | Instrumentation work package 235 | WBS.05.04 | Instrumentation | Area B | 2025-11-07 | 2026-01-13 |  |  | 67 | 890.4 | 0 | Not Started | 2025-09-30
A0236 | Civil work package 236 | WBS.05.04 | Civil | Area C | 2025-05-30 | 2025-07-19 | 2025-05-30 |  | 50 | 1304.7 | 0.9869 | In Progress | 2025-09-30
A0237 | Mechanical work package 237 | WBS.05.04 | Mechanical | Area C | 2025-07-18 | 2025-11-14 | 2025-07-18 |  | 119 | 1200 | 0.5981 | In Progress | 2025-09-30
A0238 | Piping work package 238 | WBS.05.04 | Piping | Area C | 2025-10-05 | 2025-11-19 |  |  | 45 | 1243 | 0 | Not Started | 2025-09-30
A0239 | Electrical work package 239 | WBS.05.04 | Electrical | Area C | 2025-04-13 | 2025-08-21 | 2025-04-13 |  | 130 | 560.4 | 0.96 | In Progress | 2025-09-30
A0240 | Instrumentation work package 240 | WBS.05.04 | Instrumentation | Area C | 2025-01-20 | 2025-03-27 | 2025-01-20 | 2025-03-27 | 66 | 1203.4 | 1 | Complete | 2025-09-30
A0241 | Civil work package 241 | WBS.05.05 | Civil | Area A | 2025-04-27 | 2025-09-12 | 2025-04-27 |  | 138 | 1233.7 | 0.96 | In Progress | 2025-09-30
A0242 | Mechanical work package 242 | WBS.05.05 | Mechanical | Area A | 2025-08-29 | 2025-11-12 | 2025-08-29 |  | 75 | 1760.1 | 0.3655 | In Progress | 2025-09-30
A0243 | Piping work package 243 | WBS.05.05 | Piping | Area A | 2025-05-06 | 2025-09-16 | 2025-05-06 | 2025-09-16 | 133 | 582.6 | 1 | Complete | 2025-09-30
A0244 | Electrical work package 244 | WBS.05.05 | Electrical | Area A | 2025-12-28 | 2026-03-01 |  |  | 63 | 1581.1 | 0 | Not Started | 2025-09-30
A0245 | Instrumentation work package 245 | WBS.05.05 | Instrumentation | Area A | 2025-01-11 | 2025-04-07 | 2025-01-11 | 2025-04-07 | 86 | 598.2 | 1 | Complete | 2025-09-30
A0246 | Civil work package 246 | WBS.05.05 | Civil | Area B | 2026-01-24 | 2026-03-17 |  |  | 52 | 215.8 | 0 | Not Started | 2025-09-30
A0247 | Mechanical work package 247 | WBS.05.05 | Mechanical | Area B | 2025-02-15 | 2025-07-04 | 2025-02-15 | 2025-07-04 | 139 | 1231 | 1 | Complete | 2025-09-30
A0248 | Piping work package 248 | WBS.05.05 | Piping | Area B | 2025-05-22 | 2025-08-12 | 2025-05-22 |  | 82 | 1411.1 | 0.9913 | In Progress | 2025-09-30
A0249 | Electrical work package 249 | WBS.05.05 | Electrical | Area B | 2025-09-17 | 2026-01-09 | 2025-09-17 |  | 114 | 488.4 | 0.1025 | In Progress | 2025-09-30
A0250 | Instrumentation work package 250 | WBS.05.05 | Instrumentation | Area B | 2026-02-18 | 2026-05-31 |  |  | 102 | 1359 | 0 | Not Started | 2025-09-30
A0251 | Civil work package 251 | WBS.06.01 | Civil | Area C | 2025-07-28 | 2025-09-01 | 2025-07-28 |  | 35 | 320.8 | 0.96 | In Progress | 2025-09-30
A0252 | Mechanical work package 252 | WBS.06.01 | Mechanical | Area C | 2025-04-05 | 2025-07-05 | 2025-04-05 |  | 91 | 89.5 | 0.96 | In Progress | 2025-09-30
A0253 | Piping work package 253 | WBS.06.01 | Piping | Area C | 2025-08-14 | 2025-10-18 | 2025-08-14 |  | 65 | 1682.6 | 0.639 | In Progress | 2025-09-30
A0254 | Electrical work package 254 | WBS.06.01 | Electrical | Area C | 2025-08-12 | 2025-12-24 | 2025-08-12 |  | 134 | 928.9 | 0.3193 | In Progress | 2025-09-30
A0255 | Instrumentation work package 255 | WBS.06.01 | Instrumentation | Area C | 2026-01-31 | 2026-05-26 |  |  | 115 | 1125.6 | 0 | Not Started | 2025-09-30
A0256 | Civil work package 256 | WBS.06.01 | Civil | Area A | 2025-02-24 | 2025-05-11 | 2025-02-24 |  | 76 | 864.7 | 0.96 | In Progress | 2025-09-30
A0257 | Mechanical work package 257 | WBS.06.01 | Mechanical | Area A | 2025-02-09 | 2025-04-22 | 2025-02-09 |  | 72 | 1699.8 | 0.9742 | In Progress | 2025-09-30
A0258 | Piping work package 258 | WBS.06.01 | Piping | Area A | 2025-10-06 | 2026-02-22 |  |  | 139 | 1133.6 | 0 | Not Started | 2025-09-30
A0259 | Electrical work package 259 | WBS.06.01 | Electrical | Area A | 2025-01-11 | 2025-04-01 | 2025-01-11 |  | 80 | 587.5 | 0.96 | In Progress | 2025-09-30
A0260 | Instrumentation work package 260 | WBS.06.01 | Instrumentation | Area A | 2025-06-02 | 2025-09-27 | 2025-06-02 | 2025-09-27 | 117 | 1201.9 | 1 | Complete | 2025-09-30
A0261 | Civil work package 261 | WBS.06.02 | Civil | Area B | 2025-05-17 | 2025-09-18 | 2025-05-17 | 2025-09-18 | 124 | 847.8 | 1 | Complete | 2025-09-30
A0262 | Mechanical work package 262 | WBS.06.02 | Mechanical | Area B | 2025-05-23 | 2025-08-30 | 2025-05-23 |  | 99 | 718.4 | 0.96 | In Progress | 2025-09-30
A0263 | Piping work package 263 | WBS.06.02 | Piping | Area B | 2025-07-10 | 2025-08-26 | 2025-07-10 |  | 47 | 1611 | 0.96 | In Progress | 2025-09-30
A0264 | Electrical work package 264 | WBS.06.02 | Electrical | Area B | 2025-07-01 | 2025-09-06 | 2025-07-01 |  | 67 | 1244.6 | 0.9663 | In Progress | 2025-09-30
A0265 | Instrumentation work package 265 | WBS.06.02 | Instrumentation | Area B | 2025-10-28 | 2025-12-13 |  |  | 46 | 915.2 | 0 | Not Started | 2025-09-30
A0266 | Civil work package 266 | WBS.06.02 | Civil | Area C | 2025-01-19 | 2025-04-05 | 2025-01-19 |  | 76 | 355.2 | 0.96 | In Progress | 2025-09-30
A0267 | Mechanical work package 267 | WBS.06.02 | Mechanical | Area C | 2025-02-24 | 2025-07-18 | 2025-02-24 | 2025-07-18 | 144 | 620 | 1 | Complete | 2025-09-30
A0268 | Piping work package 268 | WBS.06.02 | Piping | Area C | 2025-06-20 | 2025-08-29 | 2025-06-20 |  | 70 | 1011.2 | 0.96 | In Progress | 2025-09-30
A0269 | Electrical work package 269 | WBS.06.02 | Electrical | Area C | 2025-07-14 | 2025-09-18 | 2025-07-14 |  | 66 | 526.1 | 0.96 | In Progress | 2025-09-30
A0270 | Instrumentation work package 270 | WBS.06.02 | Instrumentation | Area C | 2025-09-12 | 2025-10-28 | 2025-09-12 |  | 46 | 843.8 | 0.4262 | In Progress | 2025-09-30
A0271 | Civil work package 271 | WBS.06.03 | Civil | Area A | 2025-09-29 | 2025-11-22 | 2025-09-29 |  | 54 | 759.6 | 0.027 | In Progress | 2025-09-30
A0272 | Mechanical work package 272 | WBS.06.03 | Mechanical | Area A | 2025-08-23 | 2026-01-04 | 2025-08-23 |  | 134 | 304.7 | 0.2749 | In Progress | 2025-09-30
A0273 | Piping work package 273 | WBS.06.03 | Piping | Area A | 2026-02-15 | 2026-04-03 |  |  | 47 | 875.8 | 0 | Not Started | 2025-09-30
A0274 | Electrical work package 274 | WBS.06.03 | Electrical | Area A | 2025-05-08 | 2025-07-01 | 2025-05-08 |  | 54 | 1390.3 | 0.96 | In Progress | 2025-09-30
A0275 | Instrumentation work package 275 | WBS.06.03 | Instrumentation | Area A | 2026-03-03 | 2026-05-20 |  |  | 78 | 1503.3 | 0 | Not Started | 2025-09-30
A0276 | Civil work package 276 | WBS.06.03 | Civil | Area B | 2026-01-08 | 2026-03-31 |  |  | 82 | 1536.8 | 0 | Not Started | 2025-09-30
A0277 | Mechanical work package 277 | WBS.06.03 | Mechanical | Area B | 2025-01-14 | 2025-04-11 | 2025-01-14 |  | 87 | 1262.9 | 0.96 | In Progress | 2025-09-30
A0278 | Piping work package 278 | WBS.06.03 | Piping | Area B | 2025-12-17 | 2026-02-18 |  |  | 63 | 442.4 | 0 | Not Started | 2025-09-30
A0279 | Electrical work package 279 | WBS.06.03 | Electrical | Area B | 2025-11-20 | 2026-01-06 |  |  | 47 | 1375.9 | 0 | Not Started | 2025-09-30
A0280 | Instrumentation work package 280 | WBS.06.03 | Instrumentation | Area B | 2025-02-13 | 2025-05-12 | 2025-02-13 |  | 88 | 213.6 | 0.96 | In Progress | 2025-09-30
A0281 | Civil work package 281 | WBS.06.04 | Civil | Area C | 2025-12-19 | 2026-05-11 |  |  | 143 | 204.4 | 0 | Not Started | 2025-09-30
A0282 | Mechanical work package 282 | WBS.06.04 | Mechanical | Area C | 2025-12-13 | 2026-04-06 |  |  | 114 | 166.4 | 0 | Not Started | 2025-09-30
A0283 | Piping work package 283 | WBS.06.04 | Piping | Area C | 2025-12-17 | 2026-05-07 |  |  | 141 | 776.8 | 0 | Not Started | 2025-09-30
A0284 | Electrical work package 284 | WBS.06.04 | Electrical | Area C | 2026-03-02 | 2026-06-12 |  |  | 102 | 695.4 | 0 | Not Started | 2025-09-30
A0285 | Instrumentation work package 285 | WBS.06.04 | Instrumentation | Area C | 2025-02-05 | 2025-05-27 | 2025-02-05 | 2025-05-27 | 111 | 496.1 | 1 | Complete | 2025-09-30
A0286 | Civil work package 286 | WBS.06.04 | Civil | Area A | 2025-03-08 | 2025-07-09 | 2025-03-08 |  | 123 | 546.8 | 0.96 | In Progress | 2025-09-30
A0287 | Mechanical work package 287 | WBS.06.04 | Mechanical | Area A | 2025-11-23 | 2026-01-30 |  |  | 68 | 80.2 | 0 | Not Started | 2025-09-30
A0288 | Piping work package 288 | WBS.06.04 | Piping | Area A | 2025-05-21 | 2025-07-02 | 2025-05-21 |  | 42 | 699.6 | 0.96 | In Progress | 2025-09-30
A0289 | Electrical work package 289 | WBS.06.04 | Electrical | Area A | 2025-07-11 | 2025-11-27 | 2025-07-11 |  | 139 | 729 | 0.6037 | In Progress | 2025-09-30
A0290 | Instrumentation work package 290 | WBS.06.04 | Instrumentation | Area A | 2025-10-05 | 2026-01-27 |  |  | 114 | 87.5 | 0 | Not Started | 2025-09-30
A0291 | Civil work package 291 | WBS.06.05 | Civil | Area B | 2025-05-14 | 2025-06-25 | 2025-05-14 |  | 42 | 1424.7 | 0.9832 | In Progress | 2025-09-30
A0292 | Mechanical work package 292 | WBS.06.05 | Mechanical | Area B | 2025-07-11 | 2025-10-03 | 2025-07-11 |  | 84 | 439.3 | 0.9088 | In Progress | 2025-09-30
A0293 | Piping work package 293 | WBS.06.05 | Piping | Area B | 2025-12-25 | 2026-05-06 |  |  | 132 | 444.6 | 0 | Not Started | 2025-09-30
A0294 | Electrical work package 294 | WBS.06.05 | Electrical | Area B | 2025-09-24 | 2025-11-28 | 2025-09-24 |  | 65 | 315 | 0.1306 | In Progress | 2025-09-30
A0295 | Instrumentation work package 295 | WBS.06.05 | Instrumentation | Area B | 2025-11-08 | 2025-12-31 |  |  | 53 | 1611.2 | 0 | Not Started | 2025-09-30
A0296 | Civil work package 296 | WBS.06.05 | Civil | Area C | 2025-05-01 | 2025-09-08 | 2025-05-01 |  | 130 | 105.3 | 0.96 | In Progress | 2025-09-30
A0297 | Mechanical work package 297 | WBS.06.05 | Mechanical | Area C | 2025-08-22 | 2025-12-01 | 2025-08-22 |  | 101 | 97.1 | 0.3857 | In Progress | 2025-09-30
A0298 | Piping work package 298 | WBS.06.05 | Piping | Area C | 2025-12-04 | 2026-04-05 |  |  | 122 | 976.6 | 0 | Not Started | 2025-09-30
A0299 | Electrical work package 299 | WBS.06.05 | Electrical | Area C | 2025-01-13 | 2025-03-19 | 2025-01-13 |  | 65 | 1409.8 | 0.96 | In Progress | 2025-09-30
A0300 | Instrumentation work package 300 | WBS.06.05 | Instrumentation | Area C | 2026-01-05 | 2026-02-06 |  |  | 32 | 1625.5 | 0 | Not Started | 2025-09-30

## KPI discipline
Discipline | Activities | Budgeted Labor Units | Planned % | Actual % | Variance pts | SPI | Late Activities
Civil | 60 | 52217.7 | 0.4301 | 0.42509 | -0.0050142 | 0.98834 | 20
Electrical | 59 | 55202.5 | 0.53617 | 0.52535 | -0.010813 | 0.97983 | 19
Instrumentation | 59 | 59461.7 | 0.57296 | 0.55151 | -0.021454 | 0.96256 | 21
Mechanical | 60 | 55229.4 | 0.66077 | 0.63482 | -0.025954 | 0.96072 | 23
Piping | 60 | 55357.2 | 0.46564 | 0.44702 | -0.018616 | 0.96002 | 17
Unassigned | 1 | 1099 | 1 | 0.96 | -0.04 | 0.96 | 1

## Courbe S
Week | Planned Cum % | Actual Cum % | Forecast Cum %
2025-01-06 | 0 | 0 | 0
2025-01-13 | 0.0007947 | 0.00071701 | 0.00071701
2025-01-20 | 0.0053246 | 0.0049331 | 0.0049331
2025-01-27 | 0.014193 | 0.013227 | 0.013227
2025-02-03 | 0.02516 | 0.023482 | 0.023482
2025-02-10 | 0.037244 | 0.034768 | 0.034768
2025-02-17 | 0.050863 | 0.047462 | 0.047462
2025-02-24 | 0.065166 | 0.060792 | 0.060792
2025-03-03 | 0.079524 | 0.074205 | 0.074205
2025-03-10 | 0.094179 | 0.087822 | 0.087822
2025-03-17 | 0.10774 | 0.10038 | 0.10038
2025-03-24 | 0.12236 | 0.11391 | 0.11391
2025-03-31 | 0.13816 | 0.12853 | 0.12853
2025-04-07 | 0.15357 | 0.14276 | 0.14276
2025-04-14 | 0.16877 | 0.15682 | 0.15682
2025-04-21 | 0.18414 | 0.17102 | 0.17102
2025-04-28 | 0.19964 | 0.18536 | 0.18536
2025-05-05 | 0.21565 | 0.20017 | 0.20017
2025-05-12 | 0.23237 | 0.21565 | 0.21565
2025-05-19 | 0.24889 | 0.23095 | 0.23095
2025-05-26 | 0.26495 | 0.24582 | 0.24582
2025-06-02 | 0.28174 | 0.26135 | 0.26135
2025-06-09 | 0.29935 | 0.27766 | 0.27766
2025-06-16 | 0.31538 | 0.29248 | 0.29248
2025-06-23 | 0.33123 | 0.30714 | 0.30714
2025-06-30 | 0.34682 | 0.32155 | 0.32155
2025-07-07 | 0.36012 | 0.33384 | 0.33384
2025-07-14 | 0.37728 | 0.34945 | 0.34945
2025-07-21 | 0.39056 | 0.36176 | 0.36176
2025-07-28 | 0.40366 | 0.3739 | 0.3739
2025-08-04 | 0.41722 | 0.38647 | 0.38647
2025-08-11 | 0.43133 | 0.39955 | 0.39955
2025-08-18 | 0.4459 | 0.41304 | 0.41304
2025-08-25 | 0.4609 | 0.42692 | 0.42692
2025-09-01 | 0.4755 | 0.44049 | 0.44049
2025-09-08 | 0.49013 | 0.45402 | 0.45402
2025-09-15 | 0.50414 | 0.46697 | 0.46697
2025-09-22 | 0.5185 | 0.48009 | 0.48009
2025-09-29 | 0.53423 | 0.49279 | 0.49279
2025-10-06 | 0.55044 | 0.51999 | 0.50579
2025-10-13 | 0.56719 | 0.51999 | 0.5188
2025-10-20 | 0.58345 | 0.51999 | 0.5318
2025-10-27 | 0.59852 | 0.51999 | 0.54481
2025-11-03 | 0.61468 | 0.51999 | 0.55781
2025-11-10 | 0.63088 | 0.51999 | 0.57082
2025-11-17 | 0.64548 | 0.51999 | 0.58382
2025-11-24 | 0.6585 | 0.51999 | 0.59683
2025-12-01 | 0.67067 | 0.51999 | 0.60983
2025-12-08 | 0.68459 | 0.51999 | 0.62284
2025-12-15 | 0.6999 | 0.51999 | 0.63585
2025-12-22 | 0.71537 | 0.51999 | 0.64885
2025-12-29 | 0.73046 | 0.51999 | 0.66186
2026-01-05 | 0.7451 | 0.51999 | 0.67486
2026-01-12 | 0.76116 | 0.51999 | 0.68787
2026-01-19 | 0.77746 | 0.51999 | 0.70087
2026-01-26 | 0.79293 | 0.51999 | 0.71388
2026-02-02 | 0.8086 | 0.51999 | 0.72688
2026-02-09 | 0.82404 | 0.51999 | 0.73989
2026-02-16 | 0.83753 | 0.51999 | 0.7529
2026-02-23 | 0.85269 | 0.51999 | 0.7659
2026-03-02 | 0.86839 | 0.51999 | 0.77891
2026-03-09 | 0.88567 | 0.51999 | 0.79191
2026-03-16 | 0.90303 | 0.51999 | 0.80492
2026-03-23 | 0.91943 | 0.51999 | 0.81792
2026-03-30 | 0.93421 | 0.51999 | 0.83093
2026-04-06 | 0.94654 | 0.51999 | 0.84393
2026-04-13 | 0.95683 | 0.51999 | 0.85694
2026-04-20 | 0.96589 | 0.51999 | 0.86994
2026-04-27 | 0.97381 | 0.51999 | 0.88295
2026-05-04 | 0.98066 | 0.51999 | 0.89596
2026-05-11 | 0.98639 | 0.51999 | 0.90896
2026-05-18 | 0.99126 | 0.51999 | 0.92197
2026-05-25 | 0.9947 | 0.51999 | 0.93497
2026-06-01 | 0.99671 | 0.51999 | 0.94798
2026-06-08 | 0.99781 | 0.51999 | 0.96098
2026-06-15 | 0.99866 | 0.51999 | 0.97399
2026-06-22 | 0.99941 | 0.51999 | 0.98699
2026-06-29 | 0.99993 | 0.51999 | 1